# Multi-year School Support Plan

Division of Student Outcomes and School Quality

Office of School Improvement

December 2025

## Table of Contents

A Statewide Approach to School Improvement	1

Organizational Structure	1

Funding Priorities	1

Effective School Improvement Practices	1

School Improvement Process	2

Step 1: Current State Analysis	2

Step 2: Planning and Prioritization	2

Step 3: Implementing, Monitoring, and Accountability	2

Step 4: Progress Reporting and Reflection	3

A Systemic Multi-Year School Support Plan to Improve Student Outcomes	3

Planning Year for Newly Identified Comprehensive Support and Improvement and Additional Targeted Support and Improvement Schools	4

Required Planning Year Activities	4

Suggested Planning Year Activities	5

Strategic Use of School Improvement Grant Funds to Support the Implementation of Multi-year School Support Plans	7

Multi-Year School Support Plan Requirements by Federal Identification Status	8

Developing the Muti-year School Support Plan	11

Division and School Information	11

Stakeholder Engagement	12

Planning Year	13

Planning Year Action Plan	14

Multi-year School Support Plan	15

Addressing Resource Inequities	16

Assurance of Review and Approval	17

## A Statewide Approach to School Improvement

The Virginia Department of Education (the Department) is launching a bold, research-based redesign of how school improvement is supported across the Commonwealth. This new model is anchored in a clear theory of action, when high-quality quantitative and qualitative data are used to understand strengths and challenges in student learning, the Department can align targeted, evidence-based supports that measurably improve student outcomes.

To inform this approach, the Department conducted a comprehensive review of high-performing state education agencies across the nation. The analysis identified key practices associated with improved student outcomes. Drawing on these insights, the Department is focusing on the following critical elements:

### Organizational Structure

The Department is implementing a strategic realignment of offices, roles, and responsibilities to improve coherence, collaboration, and operational efficiency. These structural adjustments are designed to streamline communication and increase collaboration to ensure that schools and divisions experience a coordinated and responsive system of support from the Department.

### Funding Priorities

Resources are being directed toward the implementation of evidence-based practices. Leadership is empowering school and division leaders with more autonomy and flexibility to maximize every dollar for students, while requiring clear demonstration of returns on investments that directly lead to improved student outcomes.

### Effective School Improvement Practices

School improvement is the responsibility of the entire Department. By engaging subject-matter experts from across offices, the Department expands its capacity to deliver high-quality support statewide and increases the depth of expertise available to schools and divisions. This cross-department approach ensures that every school and division benefits from a research-grounded, data-informed, and coordinated system of support.

School Improvement Process

The school improvement approach is grounded in a four-step process for school success. This process is designed to identify strengths, analyze needs, plan strategically, and monitor progress with rigor and transparency.

### Step 1: Current State Analysis

This step establishes a clear, evidence-based understanding of a school or division’s performance, strengths, and challenges. Key actions include:

- Needs assessment to identify specific areas where the school or division is not meeting expectations.

- Asset mapping to identify and document existing strengths and resources within the division, school, and community.

- Root cause analysis to uncover underlying reasons for performance challenges.

- Resource allocation review to assess how funds are deployed, evaluate the return on investment, and identify any disparities in funding, staffing, or materials that may impede improvement efforts.

### Step 2: Planning and Prioritization

This step transforms finding from the current state analysis into a focused, actionable improvement plan. Key actions include:

- Developing a multi-year school support plan to directly address root causes and leverage assets (from the asset mapping process) to support school improvement.

- Prioritizing needs based on impact, feasibility (budget, time, personnel, etc.), and urgency.

- Establishing specific, measurable, achievable, and time-bound goals.

- Selecting evidence-based interventions and creating a detailed funding and staffing plan for execution.

### Step 3: Implementing, Monitoring, and Accountability

This step ensures the improvement plan is executed as intended and that progress is regularly measured. Key actions include:

- Developing clear, outcome-based monitoring protocols defining implementation checks (are we doing what we said we would do?) and progress checks (is it working?).

- Implementing monitoring protocols with regular site visits, data reviews, and check-ins to provide timely, actionable feedback to school and division leadership.

### Step 4: Progress Reporting and Reflection

This step focuses on transparent communication of progress towards defined goals. Key actions include:

- Quarterly reporting on implementation status, interim progress data, and next steps.

- Annual reporting summarizing progress, highlighting improvements in student outcomes, and detailing successes and ongoing challenges.

This statewide approach reflects a commitment to data-informed decision-making, strong cross-department collaboration, and evidence-based action. Together, these elements create a robust and sustainable model for improving teaching, learning, and student outcomes across the Commonwealth.

A Systemic Multi-Year School Support Plan to Improve Student Outcomes

Research suggests that lasting improvement in schools takes time, focus, and consistent support. A multi-year support plan gives schools the time they need to move beyond short-term fixes and address the root causes of challenges that impact student learning. Planning over multiple years enables schools to make stronger instructional changes, learn from what works, and build the skills and systems necessary to lead to long-term success for students. A multi-year school support plan helps schools by:

- Giving improvement time to work: Evidence-based interventions typically require three to five years to yield sustainable improvements in student outcomes.

- Using resources strategically: Planning ahead helps schools and divisions use time, talent, and funding effectively, aligning operations and practices to improve efficiency, maximize return on investment, and achieve meaningful improvements in student outcomes.

- Building trust and clarity: Families and communities are actively involved in planning, which builds confidence that the school is committed to long-term success and garners lasting support for improvement efforts.

- Staying focused: When a school works toward accomplishing well-defined goals over several years, they increase the likelihood of making measurable sustained impact on improving student outcomes.

The Every Student Succeeds Act provides states with flexibility to design and implement school improvement strategies that are responsive to local needs and grounded in evidence-based practices. One such provision allows states to offer a dedicated planning year to schools newly identified for Comprehensive Support and Improvement or Additional Targeted Support and Improvement. This planning year serves as a foundational phase, enabling schools to engage in a thoughtful and data-informed process before launching their multi-year improvement efforts.

Beginning with the 2025–2026 school year, the Department will require all newly identified Comprehensive Support and Improvement or Additional Targeted Support and Improvement Schools to participate in a planning year as defined in the Virginia Consolidated State Plan. This ensures that school improvement strategies are deeply rooted in a clear understanding of each school’s unique context, strengths, and challenges to develop a clear, evidence-based path forward.

### Planning Year for Newly Identified Comprehensive Support and Improvement and Additional Targeted Support and Improvement Schools

During the planning year, school divisions may decide to engage in one or more planning year activities designed to uncover the root causes of underperformance. Allowable expenses using School improvement Grant funds include:

- conducting a needs assessment;

- identifying resource inequities;

- monitoring student outcomes across all indicators in the School Performance and Support Framework;

- engaging families and community;

- rigorously reviewing external providers;

- evaluating staffing models;

- reviewing and selecting instructional programs;

- providing professional development and supports; and

- implementing other planning activities as needed.

These activities are intended to identify systemic barriers to student success and to inform the selection of evidence-based interventions that are both targeted and sustainable. Some planning year activities are required and others are suggested.

### Required Planning Year Activities

#### Conduct a Needs Assessment

The needs assessment is the cornerstone of developing the Multi-year School Support Plan, serving as a comprehensive diagnostic tool to help identify the root causes of underperformance. This process involves analyzing multiple sources of quantitative and qualitative data aligned to the School Performance and Support Framework to identify strengths, challenges, and gaps in student outcomes. According to the Every Student Succeeds Act, the needs assessment must be grounded in evidence and informed by input from educators, families, and community members. This process establishes a clear, shared understanding of the school’s current context, which allows for targeted and strategic action planning.

#### Identify Resource Inequities

The Every Student Succeeds Act requires that Comprehensive Support and Improvement and Additional Targeted Support and Improvement Schools identify and address resource inequities that may contribute to disparities in student achievement. This work involves examining how financial, human, and material resources are distributed within the school and among schools. Key features include analyzing access to experienced teachers, advanced coursework, technology, and support services. Identifying these disparities is essential to ensuring that all students have the opportunity to succeed. The findings from this analysis inform strategic decisions about reallocating resources to more effectively support student learning and advance school improvement goals.

#### Monitor Student Outcomes Across All Accountability Indicators

Monitoring student outcomes across all accountability indicators is critical for understanding how well the school is serving all students. During the planning year, schools will establish and implement protocols to monitor disaggregated student outcomes across all indicators. This approach ensures that improvement efforts are proactive, forward-looking, and informed by data, allowing educators to proactively anticipate and respond to the needs of all learners. It also helps educators establish clear, measurable goals and interim benchmarks aligned with state accountability expectations and continuous improvement.

### Suggested Planning Year Activities

#### Engage Families and Community

Family and community engagement is a foundational element of effective school improvement planning. The Every Student Succeeds Act emphasizes the importance of meaningful stakeholder involvement in both the planning and implementation phases. During the planning year, schools create structures for ongoing dialogue with families, community organizations, businesses, higher education, and local leaders to ensure that the support plan reflects shared priorities. This approach builds trust, fosters collaboration, and strengthens the school’s capacity to meet the holistic needs of students.

#### Rigorously Review External Providers

When schools choose to partner with external providers such as consultants, curriculum vendors, or professional development organizations, the Every Student Succeeds Act requires that these providers be rigorously vetted for quality and evidence of effectiveness. During the planning year, schools establish criteria for selecting providers that align with their identified needs and improvement goals. This includes reviewing research, and evaluating past performance, deliverables, and outcomes. A rigorous review process helps schools avoid ineffective or misaligned partnerships and ensures that external support contributes meaningfully to student outcomes.

#### Evaluate Staffing Models

Staffing plays a critical role in school improvement, and the Every Student Succeeds Act encourages schools to examine whether their current staffing models support access to high-quality instruction. During the planning year, schools analyze teacher licensure and qualifications, turnover rates, leadership structures, and staff deployment to determine what is working well and what changes are needed. This evaluation may lead to strategies such as strategic staffing, targeted recruitment and retention strategies, professional learning experiences, or coaching. Aligning staffing models with student needs and improvement priorities allows educators to establish a strong foundation for instructional excellence and student success.

#### Review and Select Instructional Programs

Reviewing curricula, instructional materials, and program for standards alignment, appropriateness to the school context, and overall quality is essential for establishing a strong instructional base. The Every Student Succeeds Act requires that interventions and curricula used in school improvement be evidence-based. Educators can review instructional materials vetted by Virginia educators for alignment to standards on the Department’s textbook and instructional materials site, using the Department’s textbook review process. Schools can identify and select instructional programs that are grounded in evidence, build on existing strengths, and directly address findings in the needs assessment. This process ensures that instructional materials are aligned, relevant, and capable of accelerating student learning.

#### Provide Professional Development and Supports

Professional development is essential for equipping educators with the knowledge and skills needed to implement the school support plan effectively. During the planning year, schools identify professional learning needs based on the findings of the needs assessment and the instructional shifts required by selected interventions. The Every Student Succeeds Act emphasizes that professional development must be sustained, intensive, collaborative, and aligned with school improvement goals. This activity includes planning for job-embedded coaching, collaborative planning time, and training on new instructional programs or data systems. By investing in high-quality professional learning, schools build the internal capacity necessary to drive and sustain improvement efforts over time.

#### Implement Other Planning Activities as Needed

In addition to the core planning year activities outlined by the Every Student Succeeds Act, schools may identify other planning tasks that are critical to their local context. These may include developing communication strategies, refining school climate initiatives, strengthening systems of support, or aligning improvement efforts with other division or state initiatives. The flexibility to implement additional planning activities allows schools to address unique challenges and opportunities that may not be captured through a standard process. These activities, while varied, must still align with the federal emphasis on evidence-based practices, stakeholder engagement, and continuous school improvement. By customizing the planning year to meet their specific needs, schools can ensure that their support plans are both comprehensive and contextually relevant.

### Strategic Use of School Improvement Grant Funds to Support the Implementation of Multi-year School Support Plans

School improvement grant funds are designed to support data-informed, evidenced-based improvement efforts included in the Multi-year School Support Plan. As divisions support schools in implementing these plans, grant funding may be strategically used to align resources with identified needs, strengthen implementation, and support improved outcomes for students.

For Comprehensive Support and Improvement, Additional Targeted Support and Improvement, and Targeted Support and Improvement Schools, allowable uses of School Improvement Grant funds may be incorporated into the Multi-year School Support Plan to address prioritized needs as identified through the needs assessment process.

Allowable expenditures for multi-year school support planning and implementation that were not identified as part of the planning year may include, but are not limited to:

- evidence-based strategies

- equipment

- pay beyond contract hours

- professional learning materials and supplies

- professional and consulting services

- software licensing

- high-quality tutoring and interventions

- extended learning opportunities

- parent and family engagement activities

- division-level activities to support the implementation of the Multi-year School Support Plan

The full list of allowable and unallowable expenditures is detailed in the school improvement grant application.

### Multi-Year School Support Plan Requirements by Federal Identification Status

The Virginia Consolidated State Plan and Virginia Code (8VAC20-132-280) describe specific requirements for schools with federal designations in the development of the Multi-year School Support Plan. Table 1 summarizes these requirements by federal identification status and planning questions. This table is intended to provide clarity and support educators in understanding the actions required to meet federal and state expectations.

#### Table 1: Summary of requirements by federal identification status.

| School Federal Identification Status | Does the school have a planning year? | Who conducts the needs assessment? | Who develops the multi-year school support plan? | How many evidence-based interventions are required? | Is the plan required to identify & address resource inequities? | Who must review the multi-year school support plan? | Who must approve the multi-year school support plan? |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Newly Identified Comprehensive Support and Improvement – Low Performing | Yes | Division for the School | Division for the School | At least Four | Yes | Local School Board | School, Division, and State |
| Newly Identified Comprehensive Support and Improvement – Additional Targeted Support and Improvement | Yes | Division for the School | Division for the School | At least Four | Yes | Local School Board | School, Division, and State |
| Newly Identified Comprehensive Support and Improvement – Federal Graduation Indicator | Yes | Division for the School | Division for the School | At least Four | Yes | Local School Board | School, Division, and State |
| Newly Identified Comprehensive Support and Improvement – More Rigorous Interventions | No | Division for the School | Division for the School | At least Four | Yes | Local School Board | School, Division, and State |
| Continuing Comprehensive Support and Improvement | No | Division for the School | Division for the School | At least Four | Yes | Local School Board | School, Division, and State |
| Continuing Comprehensive Support and Improvement – More Rigorous Interventions | No | Division for the School | Division for the School | At least Four | Yes | Local School Board | School, Division, and State |
| Continuing Additional Targeted Support and Improvement | No | School | School | At least Two | Yes | N/A | Local School Board and Division |
| Targeted Support and Improvement Schools | No | School | School | At least Two | No | N/A | Local School Board and Division |

Developing the Muti-year School Support Plan

A well-developed and implemented Multi-year School Support Plan is essential for sustained improvement. The school division identifies a lead who is responsible for facilitating the completion and submission of the Multi-year School Support Plan, including stakeholder engagement. The division lead will be the point of contact for all communications regarding the Multi-year School Support Plan. Complete table 2 to provide information about the division and school.

Division and school information (table 2) and stakeholder engagement (table 3) must be completed for all schools. Planning year activities (tables 4 and 5) must be completed by all newly identified Comprehensive Support and Improvement and Additional Targeted Support and Improvement Schools.

### Division and School Information

#### Table 2: Division and School Information

| Information Needed | Enter Information Below |
| --- | --- |
| School Year | 2026 - 2027 |
| Division Name | Roanoke City Public Schools |
| Division Superintendent | Verletta White |
| School Name | Preston Park Elementary |
| Grades Served | PK-5 |
| Principal Name | Tracey Hoffman |
| Principal Email | thoffman@rcps.info |
| Division Multi-year School Support Plan Lead Name and Title | Kevin G Bowman, Supervisor, Targeted School Improvement Supervisor |
| Division Multi-year School Support Plan Lead Email | kevinbowman@rcps.info |

### Stakeholder Engagement

Developing the plan with stakeholders is required and includes teachers, school leaders, community partners, parents, students, and representatives from business, higher education, or the military. Actively involving stakeholders supports purposeful planning, builds shared ownership, and helps translate the plan from intent to action, leading to improved student outcomes.

#### Table 3: Stakeholder engagement

Identify the stakeholder group represented, name, email department/office/organization, and title for each stakeholder. Add or remove rows as necessary.

| Stakeholder Representation | Name | Email | Organization, Department, or Office | Title |
| --- | --- | --- | --- | --- |
| School Staff | Eric Fisher | efisher@rcps.info | Preston Park | Outgoing Principal |
|  | Stacy Orris | sorris@rcps.info | Preston Park | Assistant Principal |
|  | Morgan Hill | Mchill@rcps.info | Preston Park | Targeted School Improvement Mentor |
|  | Tricia Willhite | Twillhite@rcps.info | Preston Park | Instructional Coach |
|  | April Small | amsmall@rcps.info | Preston Park | Reading Specialist |
|  | Jessica Fasnacht | jfasnacht@rcps.info | Preston Park | EL Teacher |
|  | Jennifer Ragland | jragland@rcps.info | Preston Park | EL Teacher |
|  | Laura Canales | lcanales@rcps.info | Preston Park | EL Teacher |
|  | Tracey Hoffman | thoffman@rcps.info | Preston Park | Incoming Principal |
| Central Office Staff | Kevin Bowman | Kevinbowman@ | Academics & Instruction | Supervisor |
|  | Lori Wimbush | lwimbush@rcps.info | Academics & Instruction | Assistant Superintendent |
|  | Archie Freeman | afreeman@rcps.info | Academics & Instruction | Chief Instructional & Administrative Officer |
|  | Cynthia Williams | cynthiawilliams@ | Academics & Instruction | Chief Academics & Accountability Officer |
|  | Wendy Durham | wdurham@rcps.info | Academics & Instruction | Executive Director |
|  | Jesse Mazur | jmazur@rcps.info | Academics & Instruction | Executive Director |
|  | Jonathan Schulz | jshulz@rcps.info | Academics & Instruction | Executive Director |
|  | Nicholas Pontius | npontius@rcps.info | Academics & Instruction | Executive Director |
|  | Elizabeth Schenkel | eschenkel@rcps.info | Academics & Instruction | Supervisor |

Planning Year

All newly identified Comprehensive Support and Improvement and Additional Targeted Support and Improvement Schools are required to engage in a planning year. Complete table 4 to describe activities that will occur during the planning year. If a planning year is not required, then proceed to table 6.

#### Table 4: Summary of Planning Year Activities

For each planning year activity, provide a brief summary of (1) what the division plans to do to support the school, (2) why the activity is important, and (3) how the activity will contribute to improved student outcomes.

| Required Planning Year Activities The activities listed below are required to be completed during the planning year. |  |
| --- | --- |
| Conduct a needs assessment | Roanoke City Public Schools central office will support Preston Park Elementary by guiding the implementation of a comprehensive needs assessment aligned to the Virginia Support Framework. This includes supporting the analysis of multiple data sources academic (literacy, math, science), attendance, staffing collaboration, professional learning effectiveness, and school climate data and facilitating structured stakeholder engagement with families, staff, and leadership teams. Division staff will ensure that needs assessment findings are explicitly connected to root causes and SMART goals within the MYSSP across Academic, Staffing, Professional Learning, and School Climate domains. A high-quality needs assessment is foundational to continuous improvement and ensures that school improvement efforts are grounded in evidence rather than assumptions. Both the CSSP framework and the RCPS Strategic Plan emphasize data-informed decision-making and stakeholder voice to accurately identify barriers to student success, particularly for English learners and other historically underserved student groups. Without a rigorous needs assessment, improvement strategies risk being misaligned to actual student and school needs. By identifying priority needs and root causes, the school and division can target instructional supports, professional learning, and climate interventions more precisely. This leads to stronger Tier 1 instruction, more effective interventions, and improved alignment of resources resulting in gains in literacy, math achievement, student engagement, and attendance as outlined in Preston Park’s SMART goals and the division’s Academic & Post-Secondary Success pathway. |
| Identify resource inequities | The division will partner with school leadership to examine resource allocation through an equity lens, including staffing assignments, access to instructional supports, professional learning opportunities, and intervention structures. This includes reviewing the master schedule, collaboration structures for EL and special education staff, and access to evidence-based programs (e.g., HQIM, Project GLAD, literacy interventions). Division supervisors will support adjustments to ensure resources are aligned to student need, particularly given Preston Park’s high proportion of English learners. The RCPS Strategic Plan explicitly calls for the intentional allocation of resources to eliminate achievement gaps and ensure equitable access to high-quality instruction. Identifying resource inequities during the planning year allows the division and school to proactively address systemic barriers such as insufficient collaboration time, limited intervention access, or misaligned staffing before they negatively impact student performance. When staffing, instructional materials, and professional learning are aligned to student need, teachers are better equipped to deliver rigorous, inclusive instruction. Addressing inequities strengthens support for English learners, improves instructional coherence, and increases the effectiveness of Tier 1 and targeted interventions contributing to higher achievement, reduced gaps between student groups, and improved engagement and attendance. |
| Monitor student outcomes across all indicators in the School Performance and Support Framework | Roanoke City Public Schools central office will support ongoing monitoring of student outcomes across academic achievement, growth, attendance, and school climate indicators aligned to the School Performance and Support Framework. This includes supporting regular data reviews of formative and summative assessments (e.g., VALLSS, MAP, SOLs), attendance data, and walkthrough and observation evidence. Division staff will assist school leadership in using these data to evaluate progress toward MYSSP goals and to make timely instructional and operational adjustments. Continuous monitoring ensures that improvement efforts remain responsive and effective. The RCPS Strategic Plan emphasizes progress monitoring and accountability to ensure strategies are producing the intended impact. Monitoring across multiple indicators not just test scores provides a more complete picture of student success and school effectiveness. Regular monitoring allows the school and division to identify trends early, respond to emerging needs, and refine instructional practices in real time. This leads to improved instructional quality, stronger intervention alignment, reductions in chronic absenteeism, and sustained academic growth directly supporting Preston Park’s MYSSP goals and the division’s long-term targets for literacy, growth, and well-being. |
| Suggested Planning Year Activities The activities listed below are not required. If the school division plans to engage in any of these activities and intends to use school improvement grant funding to support them, then the division must complete the information in the table below. |  |
| Engage families and community | - Host multilingual family learning nights focused on literacy and math strategies families can use at home - Establish a family advisory group that meets quarterly to provide input on school improvement priorities - Partner with community organizations to support attendance, tutoring, or wraparound services - Conduct family surveys and listening sessions to understand barriers to engagement and trust |
| Review external providers |  |
| Evaluate staffing models | - Analyze current staffing assignments to determine alignment with student needs (e.g., English learners, intervention groups) - Review collaboration time and caseloads for instructional staff - Pilot alternative staffing structures (e.g., push-in EL support, co-teaching, intervention blocks) - Engage teachers and staff in feedback cycles regarding effectiveness and sustainability - 1 x Specialist Allocation for reading plans according to the VLA/VALLSS results (Title 1 funding) |
| Review and select instructional programs | - Conduct an instructional materials audit to assess alignment to standards and student needs - Review evidence-based literacy, math, and intervention programs - Pilot selected programs with fidelity checks and feedback loops - Involve teachers and instructional leaders in selection decisions - Review HQIMs and implement division and state required curriculum |
| Provide professional development and supports | - Deliver job-embedded professional learning aligned to identified needs (e.g., literacy, EL strategies, data use) - Provide coaching cycles focused on instructional improvement - Create collaborative planning structures to support implementation - Monitor professional learning impact through observations and student data |
| Implement other planning activities as needed. Provide a description of the planning activities |  |

#### Table 5: Planning Year Action Plan

Complete an action plan for each activity identified in table 4. For each activity, identify the lead person, team members, actions steps, process owner, time frame, progress checks, measures of success, cost elements, and funding sources.

| ### Planning Year Action Plan |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Planning Year Activity (What do you plan to do?) |  |  | Family Engagement Structure Planning Year |  |  |  |  |
| Lead person (Who is responsible for ensuring the work gets done?) |  |  | Principal |  |  |  |  |
| Team Members (Who are responsible for doing the work?) |  |  | Administrators, School Leadership Team, Teachers, Staff |  |  |  |  |
| Action Step (What will be accomplished?) List the specific, sequenced steps required to complete the activity. | Process Owner (Who is responsible for ensuring the action step is complete?) Identify a single, accountability lead. | Time Frame (How long will it take?) Identify the start and end dates for each action step, including any key milestones. |  | Progress Checks (How will the team monitor progress?) Define key dates to review process, make adjustments, and confirm the work remains on track. | Measures of Success (How will the team know if the action step is complete?) Define clear, observable indicators of completion. | Cost Elements (What resources are needed to complete the action step?) | Funding Source (Where will the money come from?) |
| 1. Analyze current family engagement data and participation trends | Principal | July 2025–May 2026 Milestones: Survey completion (Aug), advisory group launch (Sept), quarterly events |  | Quarterly review of participation data and survey feedback | • Family advisory group established • Increased family participation rates • Documented feedback used in planning | Translation services, materials, event supplies | School Improvement Grant / Title I School Improvement |
| 2. Conduct family surveys and listening sessions (multilingual) 3. Plan and host academic family engagement events aligned to literacy and math |  |  |  |  |  |  |  |
| 4.Partner with community organizations to support attendance and learning |  |  |  |  |  |  |  |

| ### Planning Year Action Plan |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Planning Year Activity (What do you plan to do?) |  |  | Evaluate and Refine Staffing |  |  |  |  |
| Lead person (Who is responsible for ensuring the work gets done?) |  |  | Principal |  |  |  |  |
| Team Members (Who are responsible for doing the work?) |  |  | Administrators, Central Office |  |  |  |  |
| Action Step (What will be accomplished?) List the specific, sequenced steps required to complete the activity. | Process Owner (Who is responsible for ensuring the action step is complete?) Identify a single, accountability lead. | Time Frame (How long will it take?) Identify the start and end dates for each action step, including any key milestones. |  | Progress Checks (How will the team monitor progress?) Define key dates to review process, make adjustments, and confirm the work remains on track. | Measures of Success (How will the team know if the action step is complete?) Define clear, observable indicators of completion. | Cost Elements (What resources are needed to complete the action step?) | Funding Source (Where will the money come from?) |
| 1. Review student data and staffing assignments | Principal | July 2025–December 2025 Milestones: Analysis complete (Aug), pilot begins (Oct) |  | Monthly leadership team check-ins on implementation | • Staffing analysis completed • Revised staffing model documented • Feedback collected from staff | Substitute coverage, planning time, technical assistance, temporary staffing | School Improvement Grant / Title I School Improvement |
| 2. Analyze caseloads, schedules, and collaboration time |  |  |  |  |  |  |  |
| 3. Identify gaps or inequities in support |  |  |  |  |  |  |  |
| 4. Design revised staffing or service delivery models |  |  |  |  |  |  |  |

| ### Planning Year Action Plan |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Planning Year Activity (What do you plan to do?) |  |  | Review and select instructional programs aligned to student needs |  |  |  |  |
| Lead person (Who is responsible for ensuring the work gets done?) |  |  | Principal |  |  |  |  |
| Team Members (Who are responsible for doing the work?) |  |  | Administrators, Central Office |  |  |  |  |
| Action Step (What will be accomplished?) List the specific, sequenced steps required to complete the activity. | Process Owner (Who is responsible for ensuring the action step is complete?) Identify a single, accountability lead. | July 2025–January 2026 Milestones: Audit complete (Aug), pilot review (Nov) |  | Progress Checks (How will the team monitor progress?) Define key dates to review process, make adjustments, and confirm the work remains on track. | Measures of Success (How will the team know if the action step is complete?) Define clear, observable indicators of completion. | Cost Elements (What resources are needed to complete the action step?) | Funding Source (Where will the money come from?) |
| 1. Conduct instructional materials audit | Principal | July 2025–January 2026 Milestones: Audit complete (Aug), pilot review (Nov) |  | Pilot data reviews and instructional walkthroughs | • Materials audit completed • Selected programs aligned to standards • Implementation plan documented | Instructional materials, pilot licenses, assessment tools, central office support | School Improvement Grant / Title I School Improvement |
| 2.Review evidence-based instructional and intervention programs |  |  |  |  |  |  |  |
| 3. Pilot selected resources with fidelity checks |  |  |  |  |  |  |  |
| 4. Gather teacher feedback and student data |  |  |  |  |  |  |  |

| ### Planning Year Action Plan |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Planning Year Activity (What do you plan to do?) |  |  | Provide targeted professional development and instructional supports |  |  |  |  |
| Lead person (Who is responsible for ensuring the work gets done?) |  |  | Principal |  |  |  |  |
| Team Members (Who are responsible for doing the work?) |  |  | Administrators, Central Office, School Instructional Leadership |  |  |  |  |
| Action Step (What will be accomplished?) List the specific, sequenced steps required to complete the activity. | Process Owner (Who is responsible for ensuring the action step is complete?) Identify a single, accountability lead. | July 2025–January 2026 Milestones: Audit complete (Aug), pilot review (Nov) |  | Progress Checks (How will the team monitor progress?) Define key dates to review process, make adjustments, and confirm the work remains on track. | Measures of Success (How will the team know if the action step is complete?) Define clear, observable indicators of completion. | Cost Elements (What resources are needed to complete the action step?) | Funding Source (Where will the money come from?) |
| 1. Identify professional learning needs aligned to goals | Principal | August 2025–May 2026 Milestones: PD plan finalized (Aug), mid-year review (Jan) |  | PD attendance logs, coaching notes, observation data | •PD plan implemented • Increased instructional consistency • Evidence of strategy use in classrooms | Coaches, PD providers, pay beyond contract hours, substitutes, planning materials | School Improvement Grant / Title I School Improvement |
| 2. Develop PD plan connected to selected programs and strategies |  |  |  |  |  |  |  |
| 3. Provide job-embedded PD and coaching cycles |  |  |  |  |  |  |  |
| 4. Support collaborative planning and reflection |  |  |  |  |  |  |  |

Multi-year School Support Plan

#### Table 6: Multi-year School Support Plan

Complete a support plan for each prioritized root cause from the completed needs assessment process.  For each goal, identify the 3-year goal statement, framework indicator, measurable objectives, Evidence-based Strategy, intended outcomes, the lead person, and appropriate team members. Then, identify the actions steps, process owner, time frame, progress checks, measures of success, cost elements, and funding sources.

| Multi-year School Support Plan |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3-Year Goal Statement Include the goal statement completed as part of the needs assessment process. |  |  | By 2028, Preston Park Elementary will implement and sustain a coherent, well-resourced schoolwide implementation system that ensures equitable access to high-quality Tier 1 literacy instruction for all students. This system will include an aligned master schedule that prioritizes co-teaching within Tier 1, embedded and responsive professional learning, clearly defined monitoring routines, and authentic family and community engagement. As a result, instructional delivery will be consistent across classrooms, students with disabilities and English learners will receive inclusive supports within Tier 1, and student achievement outcomes will improve across all student groups. |  |  |  |  |  |  |
| School Performance and Support Framework Alignment Select indicator that the goal addresses. |  |  | Reading Growth |  |  |  |  |  |  |
| Measurable Objectives Define objectives that support accomplishing the goal. |  |  | Measurable Objective Year 1 |  | Measurable Objective Year 2 |  |  | Measurable Objective Year 3 |  |
|  |  |  | - Increase Tier 1 literacy instructional time across all grade levels through master schedule redesign and reduced pull-out services. - Establish consistent co-teaching practices in identified high-need classrooms (high needs classroom is identified as having 50% or more of students who are classified as EL/Sped). - Implement structured professional learning cycles aligned to HQIM and literacy instruction. |  | - Increase percentage of classrooms demonstrating consistent Tier 1 instructional practices and co-teaching fidelity. - Improve implementation of reading plans through strengthened staffing and intervention coordination. - Demonstrate consistent use of monitoring routines across grade levels. |  |  | - Increase student achievement in reading across all student groups, with reductions in high-risk literacy bands according the VALLSS screener. - Sustain full implementation of Tier 1 inclusive practices and collaborative planning structures. - Demonstrate measurable improvements in school climate and family engagement participation. |  |
| Evidence-Based Strategy Describe the evidence-based strategy and the rationale for selection. Identify evidence tier. |  |  | K–3: Teach students to decode words, analyze word parts, and write/recognize words through explicit, systematic routines. Grades 4–5: Routinely use comprehension‑building practices: (A) build world/word knowledge, (B) teach students to ask/answer text‑dependent questions, (C) teach a gist routine, and (D) teach students to monitor comprehension. Rationale: The school has identified variability in training, resources, pacing, and student vocabulary as barriers. Systematic foundational skills (K–3) and daily comprehension routines (4–5), implemented with aligned planning, observation feedback, and PLC data reviews, directly address the documented needs. |  |  |  |  |  |  |
| Intended Outcomes Describe how student outcomes will improve as a result implementing the evidence-based strategy. |  |  | - Students experience consistent, high-quality Tier 1 literacy instruction across classrooms - SWD and EL students receive inclusive supports without loss of core instruction time - Reading plan implementation improves in integrity and timeliness (maximize instructional time) - Teacher practice becomes more aligned and data-driven - School climate and engagement improve, increasing student access to learning opportunities |  |  |  |  |  |  |
| Lead person (Who is responsible for ensuring the work gets done?) |  |  | Principal |  |  |  |  |  |  |
| Team Members (Who are responsible for doing the work?) |  |  | Instructional Leadership Team (ILT) members; Instructional Coaches; Reading Specialist; Grade-level Teams; District Specialists/Coordinators |  |  |  |  |  |  |
| Action Step (What will be accomplished?) List the specific, sequenced steps required to complete the activity. | Process Owner (Who is responsible for ensuring the action step is complete?) Identify a single, accountability lead. | Time Frame (How long will it take?) Identify the start and end dates for each action step, including any key milestones. |  | Progress Checks (How will the team monitor progress?) Define key dates to review process, make adjustments, and confirm the work remains on track. |  | Measures of Success (How will the team know if the action step is complete?) Define clear, observable indicators of completion. | Cost Elements (What resources are needed to complete the action step?) |  | Funding Source (Where will the money come from?) |
| Modify School Schedule to Prioritize Tier 1 and Co-Teaching | Principal | Summer 2026 – Fall 2026 (implementation), ongoing refinement |  | Quarterly schedule reviews; walkthrough data on Tier 1 access |  | Elimination of routine pull-out services during Tier 1 Co-teaching present in identified classrooms | Staffing allocations, planning time |  | Title I, School Operating Budget |
| Increase Access to Reading Specialists and Intervention Support Increase Special Education Access to Tier 1 and Co-Teaching | Principal | Summer 2026 hiring cycle; ongoing |  | Reading plan progress monitoring cycles |  | Reduced reading plan caseloads per specialist Increased completion and integrity of reading plans | Salaries for additional reading specialists |  | Title I |
| Implement Job-Embedded Professional Learning Communities (PLCs) | Targeted School Improvement Mentor/Instructional Coach | Fall 2026 – Spring 2028 (ongoing cycles) |  | PLC Agendas, and instructional rounds/priorities, structured learning observations and walkthrough data |  | Increased use of HQIM Evidence of data-informed instruction | PD materials, teacher pay beyond contract hours for extended learning |  | Title II, Title I, CSI Grant Funds |
| Establish Consistent Monitoring and Data Review Routines | Principal | Summer 2026 – 1 Session Weekly beginning in August 2026 |  | IlT Agendas and Instructional priorities, school-wide data and multi-year school support plan progress checks |  | Data cycles implemented with integrity Instructional adjustments documented | Data systems, staff time |  | Title II, Title I, CSI Grant Funds |
| Strengthen Family and Community Engagement Systems | Principal | Fall 2026 – Spring 2027 |  | Event participation data; family feedback surveys |  | Increased participation across diverse families Expanded multilingual communication beyond current methods | Translation services, family events |  | Title I |
| Strengthen Leadership Capacity and School Climate Systems | Principal/Central Office | 2026–2027 staffing cycle and ongoing |  | Discipline data reviews; climate surveys |  | Reduced discipline referrals Increased use of restorative practices | Additional AP/dean roles |  | Local / Title I (if allowable) |
| Implementation of Operation Golden Thread | Principal | Summer 2026 – Fall 2026 (implementation), ongoing refinement |  | Reading plan progress monitoring cycles IEP Goals and progress monitoring cycles |  | Reduce the number of students on reading plans and improve student achievement in reading Improve literacy outcomes for students with IEPs and student reading plans, and/or EL students who are dually identified | PD materials, teacher pay beyond contract hours for extended learning |  | Title 1, other grant funds |
| Multi-year School Support Plan |  |  |  |  |  |  |  |  |  |
| 3-Year Goal Statement Include the goal statement completed as part of the needs assessment process. |  |  | By 2028, Preston Park Elementary will implement and sustain a coherent, well-resourced schoolwide implementation system that ensures equitable access to high-quality Tier 1 mathematics instruction for all students. This system will include an aligned master schedule that prioritizes protected math instructional time and inclusive co-teaching models, job-embedded professional learning aligned to mathematics practices and data use, consistent monitoring routines, and strengthened family and community engagement. As a result, instructional delivery will be consistent across classrooms, students with disabilities and English learners will receive inclusive supports within Tier 1 mathematics, and math achievement outcomes will improve across all student groups. |  |  |  |  |  |  |
| School Performance and Support Framework Alignment Select indicator that the goal addresses. |  |  | Math Growth |  |  |  |  |  |  |
| Measurable Objectives Define objectives that support accomplishing the goal. |  |  | Measurable Objective Year 1 |  | Measurable Objective Year 2 |  |  | Measurable Objective Year 3 |  |
|  |  |  | - By December 2026, 100% of grade levels will implement a protected daily math block of at least 60 minutes, with no more than 5% of students removed during Tier 1 instruction, as measured by master schedule audits and walkthrough data. - By December 2026, 80% of classrooms will demonstrate HQIM-aligned math instruction and evidence of student discourse strategies - By June 2027, 100% of PLC teams will engage in bi-weekly math data cycles using common formative assessments, with documented instructional adjustments in at least 80% of PLC artifacts. |  | - By June 2027,100% of classrooms will consistently implement Tier 1 math instructional practices aligned to HQIM, as measured by walkthrough and observation data. - By June 2027, 100% of students identified for intervention will receive math supports aligned directly to Tier 1 content, as measured by intervention plans and lesson alignment reviews. - By June 2027, 100% of PLC teams will demonstrate consistent use of student data to adjust instruction, with documented adjustments occurring in at least 90% of PLC cycles and evidence of re-teaching or enrichment plans. |  |  | - By Spring 2028, math SOL pass rates will increase from 42% to at least 60% overall, with annual growth of at least 6 percentage points. - By Spring 2028, achievement gaps between all students and SWD/EL subgroups will decrease by at least 10 percentage points, based on SOL disaggregated data. - By June 2028, 100% of classrooms will demonstrate consistent implementation of Tier 1 math practices, aligned planning, and data-driven instruction, as measured by walkthroughs, PLC documentation, and leadership monitoring tools. |  |
| Evidence-Based Strategy Describe the evidence-based strategy and the rationale for selection. Identify evidence tier. |  |  | WWC Practice Guide 26 - Assisting Students Struggling with Mathematics: Intervention in the Elementary Grades Recommendation 1: Systematic Instruction: Provide systematic instruction during intervention to develop student understanding of mathematical ideas. Recommendation 3: Representations: Use a well-chosen set of concrete and semi-concrete representations to support students’ learning of mathematical concepts and procedures. |  |  |  |  |  |  |
| Intended Outcomes Describe how student outcomes will improve as a result implementing the evidence-based strategy. |  |  | - Students experience consistent, high-quality Tier 1 math instruction across classrooms - Students demonstrate increased conceptual understanding and problem-solving skills - SWD and EL students access grade-level math instruction with appropriate supports - Teacher use of data improves instructional responsiveness - Math achievement improves and performance gaps narrow across student groups |  |  |  |  |  |  |
| Lead person (Who is responsible for ensuring the work gets done?) |  |  | Principal |  |  |  |  |  |  |
| Team Members (Who are responsible for doing the work?) |  |  | Instructional Leadership Team (ILT) members; Instructional Coaches; Reading Specialist; Grade-level Teams; District Specialists/Coordinators |  |  |  |  |  |  |
| Action Step (What will be accomplished?) List the specific, sequenced steps required to complete the activity. | Process Owner (Who is responsible for ensuring the action step is complete?) Identify a single, accountability lead. | Time Frame (How long will it take?) Identify the start and end dates for each action step, including any key milestones. |  | Progress Checks (How will the team monitor progress?) Define key dates to review process, make adjustments, and confirm the work remains on track. |  | Measures of Success (How will the team know if the action step is complete?) Define clear, observable indicators of completion. | Cost Elements (What resources are needed to complete the action step?) |  | Funding Source (Where will the money come from?) |
| Modify School Schedule to Protect Tier 1 Math Instruction | Principal | Summer 2026 – Fall 2026; ongoing refinement |  | Quarterly schedule audits; walkthrough data focused on math blocks |  | Uninterrupted math instructional blocks across grade levels Reduced loss of math instructional time due to pull-outs | Staffing allocations, scheduling/planning time |  | Title I, Local Budget |
| Strengthen Tier 1 Math Instruction Using HQIM and Discourse Practices | Targeted School Improvement Mentor/Instructional Coach | Fall 2026 – Spring 2028 (ongoing cycles) |  | Lesson plan reviews; instructional walkthroughs; PLC artifacts |  | Increased use of math discourse strategies Evidence of conceptual understanding in student work | Instructional materials, PD resources |  | Title II, Title I |
| Implement Math Data Cycles and Common Assessments | Principal / AP/Instructional Coach/TSIM | Fall 2026 – ongoing |  | Bi-weekly PLC data meetings; quarterly benchmark reviews |  | Documented instructional adjustments based on data Increased student growth on formative and benchmark assessments | Assessment tools, data platforms |  | Local, Title 1 |
| Align Intervention and Inclusive Supports to Tier 1 Math | Principal / SPED & EL Leads | Fall 2026 – Spring 2028 |  | Intervention logs; co-teaching walkthroughs |  | Increased inclusion of SWD and EL students in Tier 1 math Improved alignment between intervention and core instruction | Staffing support, co-planning time |  | Local, Title 1 |
| Implement Job-Embedded Professional Learning for Math Instruction | TSIM/Instructional Coach | Fall 2026 – Spring 2028 |  | Coaching cycles; PLC monitoring; teacher feedback |  | Evidence of aligned instructional practices across classrooms | Stipends, PD materials |  | Title II, CSI |
| Strengthen Monitoring Routines for Math Achievement | Principal / Leadership Team | Fall 2026 – ongoing |  | Monthly leadership reviews; quarterly performance analysis |  | Consistent monitoring cycles implemented Data-driven decision-making documented | Staff time, data tools |  | Local, Title 1, CSI |
| Expand Family Engagement in Math Learning | Principal | Fall 2026 – Spring 2028 |  | Participation logs; family surveys |  | Increased attendance at math-focused family events Improved family understanding of math expectations | Materials, translation services, event costs |  | Title I, CSI |
| Multi-year School Support Plan |  |  |  |  |  |  |  |  |  |
| 3-Year Goal Statement Include the goal statement completed as part of the needs assessment process. |  |  | By June 2028, Preston Park Elementary will implement and sustain a comprehensive system to accelerate English Learner (EL) progress through equitable access to rigorous, language-rich Tier 1 and Tier 2 instruction. This will be achieved by embedding academic language development across all content areas, utilizing guided language acquisition design, and systematically monitoring EL progress. As a result, English Learners and Emerging Bilingual students will demonstrate increased proficiency in language development and content mastery, leading to improved achievement outcomes and reduced gaps between EL and non-EL student groups. |  |  |  |  |  |  |
| School Performance and Support Framework Alignment Select indicator that the goal addresses. |  |  | English Learner Progress |  |  |  |  |  |  |
| Measurable Objectives Define objectives that support accomplishing the goal. |  |  | Measurable Objective Year 1 |  | Measurable Objective Year 2 |  |  | Measurable Objective Year 3 |  |
|  |  |  | (By June 2026) Design and implement a foundational EL support system such that: - 100% of teachers integrate academic language strategies within Tier 1 instruction - Guided language acquisition design (GLAD) strategies are introduced and implemented across grade levels - Monitoring systems are established to track EL progress in both language acquisition and content learning |  | (By June 2027) Strengthen implementation of EL instructional practices such that: - Consistent academic language routines are evident across all classrooms - Teachers scaffold instruction to support EL access to grade-level content - Monitoring systems are used regularly to inform instructional adjustments and supports |  |  | Sustain a comprehensive EL support system such that: - Academic language development is embedded in all instructional practices across content areas - Teachers consistently use data to refine instruction for EL students - EL students demonstrate measurable growth in language proficiency and content achievement |  |
| Evidence-Based Strategy Describe the evidence-based strategy and the rationale for selection. Identify evidence tier. |  |  | Preston Park Elementary will implement a coordinated approach to English Learner instruction by embedding academic language development within Tier 1 instruction using guided language acquisition design. This includes integrating language objectives, structured student discourse, and scaffolded supports across content areas. The strategy is supported by research demonstrating that explicit academic language instruction and integrated language-content approaches improve both language acquisition and academic outcomes for English Learners (Evidence Tier: Strong/Moderate). |  |  |  |  |  |  |
| Intended Outcomes Describe how student outcomes will improve as a result implementing the evidence-based strategy. |  |  | - English Learners consistently engage in rigorous, language-rich instruction across all content areas - Increased use of academic language by students in speaking, writing, and collaborative learning - Improved teacher capacity to support EL students through intentional instructional practices - Increased student engagement through student voice, questioning, and use of academic discourse - Measurable growth in EL language proficiency and academic achievement across all subgroups and WIDA grade level clusters - Reduction in achievement gaps between EL and non-EL students |  |  |  |  |  |  |
| Lead person (Who is responsible for ensuring the work gets done?) |  |  | Principal |  |  |  |  |  |  |
| Team Members (Who are responsible for doing the work?) |  |  | Instructional Leadership Team (ILT) members; Instructional Coaches; Reading Specialist; Grade-level Teams; District Specialists/Coordinators |  |  |  |  |  |  |
| Action Step (What will be accomplished?) List the specific, sequenced steps required to complete the activity. | Process Owner (Who is responsible for ensuring the action step is complete?) Identify a single, accountability lead. | Time Frame (How long will it take?) Identify the start and end dates for each action step, including any key milestones. |  | Progress Checks (How will the team monitor progress?) Define key dates to review process, make adjustments, and confirm the work remains on track. |  | Measures of Success (How will the team know if the action step is complete?) Define clear, observable indicators of completion. | Cost Elements (What resources are needed to complete the action step?) |  | Funding Source (Where will the money come from?) |
| Conduct needs assessment focused on EL performance, language development, and instructional practices | Principal / EL Team | May 2026 |  | Data reviews; team meetings; EL subgroup analysis |  | Identified gaps and priorities for EL instruction | Staff time |  | Title III / Local |
| Develop clear expectations for academic language instruction throughout all content areas | Principal | July 2026 - ongoing |  | ILT agendas, school wide initiative goals (rocks), student accountability artifacts |  | Observable increased academic language in student conversation | Professional learning and development beyond contract hours |  | Title 1/SIG |
| Provide professional learning on guided language acquisition design, academic language, and student goal setting | Principal | July 2026 - ongoing |  | PLC/ILT agendas, instructional calendar, coaching logs, sign in sheets |  | Improved teacher practice, 100% teacher participation- teacher action steps | Professional learning and development beyond contract hours |  | Title 1/SIG |
| Sustain and/or implement student and family conferences and goal setting for language acquisition | Principal | August 2026 - ongoing |  | Survey audits, teacher data, goal proficiency chart – beginning, mid, end of year; student artifacts |  | Student surveys, VALSS, benchmarks, WIDA student achievement data | Staff time, master schedule |  | Title I, CSI Funds |
| Develop a strategic schedule for WIDA clusters and groups of students | Principal/EL Supervisor | July 2026 - ongoing |  | Schedule audits, academic review |  | Master schedule, testing schedule |  |  | Title 1/SIG |
| Strengthen scaffolding practices around guided language acquisition design | Principal | August 2026 - ongoing |  | Walkthroughs, observations, lesson plans, EL coaching logs |  | Aligned plans to standards and performance descriptors | Professional learning and development beyond contract hours |  | Title 1/SIG |
| Monitor student practice, engagement, and use of language | Principal | August 2026 - ongoing |  | WIDA rubric |  | WIDA performance descriptors | Professional learning and development beyond contract hours |  | Title 1/SIG |
| Sustain hybrid co-teaching model for Tier 1, Tier 2 and Tier 3 | Principal | August 2026-ongoing |  | Lesson plan audits, collaborative planning schedule, walkthroughs, observations |  | Master schedule, instructional schedule followed with integrity | Professional learning and development beyond contract hours |  | Title 1/SIG |
| Sustain and refine EL instructional practices through ongoing coaching and collaborative planning | Principal/Target School Improvement Mentor/EL and Instructional Coach | July 2026 - ongoing |  | PLC/ILT agendas, instructional calendar, coaching logs, sign in sheets |  | Student achievement data, EL progress – all academic indicators | Professional learning and development beyond contract hours |  | Title 1/SIG |

Addressing Resource Inequities

#### Table 7: Addressing Resource Inequities Plan

The Addressing Resource Inequities Plan should be completed by Comprehensive Support and Improvement and Additional Targeted Support and Improvement schools following the complete of the Resource Inequity Review.

Complete a resource inequities plan for each prioritized root cause from the completed Resource Inequity Review process.  For each area, identify the 3-year goal statement, measurable objectives, strategy, intended outcomes, the lead person, and appropriate team members. Then, identify the actions steps, process owner, time frame, progress checks, measures of success, cost elements, and funding sources.

| Addressing Resource Inequities Plan |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3-Year Goal Statement Include the goal statement completed as part of the Resource Inequity Review process. |  |  | By 2028 Preston Park will implement and sustain a master schedule that ensures equitable access to high‑quality Tier 1 literacy instruction for all students, including students with disabilities and English learners, by embedding co‑teaching models in high‑need classrooms, eliminating routine pull‑outs during Tier 1 instruction, and guaranteeing protected collaborative planning time for teachers. As a result, Tier 1 literacy instructional minutes will be consistently protected across grade levels, inclusive instructional practices will be implemented with integrity, and teacher collaboration will support stronger instructional coherence, leading to improved literacy outcomes and reduced achievement gaps for identified student groups. |  |  |  |  |  |  |
| Measurable Objectives Define objectives that support accomplishing the goal. |  |  | Measurable Objective Year 1 |  |  | Measurable Objective Year 2 |  | Measurable Objective Year 3 |  |
|  |  |  | By June 2026, Preston Park will design and pilot a revised master schedule that: Protects 100% of Tier 1 literacy instructional minutes for all students in grades K–5, with no routine pull‑outs during Tier 1 for students with disabilities or English learners; and Embeds co‑teaching models in at least 50% of identified high‑need classrooms; and Provides protected, scheduled collaborative planning time at least weekly for all grade‑level teams. |  |  | By June 2027, Preston Park will fully implement the revised master schedule across all grade levels such that: All SWD and EL students receive Tier 1 literacy instruction through inclusive/co‑taught models, rather than routine pull‑out services; 100% of high‑need classrooms are supported by a co‑teacher during Tier 1 literacy; and Collaborative planning time is consistently used for job‑embedded professional learning, as evidenced by agendas, lesson plans, and instructional adjustments aligned to literacy goals. |  | By June 2028, Preston Park will sustain an equitable master schedule that: Ensures Tier 1 literacy access is protected for all students across all grade levels; Demonstrates consistent, high‑fidelity co‑teaching practices in high‑need classrooms; and Results in measurable improvements in literacy outcomes and reduced achievement gaps for students with disabilities and English learners, as demonstrated by schoolwide and subgroup literacy data. |  |
| Strategy Describe the strategy and the rationale for selection. |  |  | Preston Park Elementary will redesign and implement a master schedule centered on equitable access to Tier 1 literacy instruction by prioritizing inclusive instructional models, protected instructional minutes, and structured collaboration time. The strategy focuses on eliminating routine pull‑out services during Tier 1 literacy, embedding co‑teaching models in high‑need classrooms, and guaranteeing protected, recurring collaborative planning time for teachers, special education staff, and English learner specialists. |  |  |  |  |  |  |
| Intended Outcomes Describe how student outcomes will improve as a result implementing the strategy. |  |  | - Students with disabilities and English learners will have equitable access to high‑quality Tier 1 literacy instruction, resulting in increased time engaged with grade‑level content and evidence‑based practices. - Students receiving inclusive Tier 1 instruction will demonstrate improved literacy achievement and growth, as reflected in schoolwide and subgroup literacy measures. - Co‑teaching models will be implemented with integrity in high‑need classrooms, strengthening inclusive instructional practices and reducing fragmentation of services. - Teachers will engage in regular, protected collaborative planning focused on literacy instruction, student data, and inclusive practices. |  |  |  |  |  |  |
| Lead person (Who is responsible for ensuring the work gets done?) |  |  | Principal |  |  |  |  |  |  |
| Team Members (Who are responsible for doing the work?) |  |  | Assistant Principal(s), Targeted School Improvement Mentor, Instructional Coach, Reading Specialist(s), Classroom Teachers |  |  |  |  |  |  |
| Action Step (What will be accomplished?) List the specific, sequenced steps required to complete the activity. | Process Owner (Who is responsible for ensuring the action step is complete?) Identify a single, accountability lead. | Time Frame (How long will it take?) Identify the start and end dates for each action step, including any key milestones. |  | Progress Checks (How will the team monitor progress?) Define key dates to review process, make adjustments, and confirm the work remains on track. | Measures of Success (How will the team know if the action step is complete?) Define clear, observable indicators of completion. |  | Cost Elements (What resources are needed to complete the action step?) |  | Funding Source (Where will the money come from?) |
| Conduct master schedule audit to identify current barriers to equitable literacy access (pull-outs, gaps, etc.) | Principal/Chief Academic Officer | May 2026 – September 2027, continuous |  | Schedule audits, academic review each 9 weeks | Resource inequity guide and planning, master schedule creation for Preston Park |  | Planning time for staff |  | SIG Funds |
| Develop and design revised master schedule prioritizing Tier 1 protection and co-teaching | Principal/Chief Academic Officer | Planning May 2026 – continuous |  | Schedule audits, co-teaching schedules provided by school leadership | Observable co-teaching practices Observation of 100% of identified students in Tier 1 literacy instruction during reading blocks |  | Planning and scheduling for staff |  | SIG Funds |
| Provide training on co-teaching models and inclusive instructional practices | Targeted School Improvement Mentor/Instructional Coach | Summer 2026 – September 2027 |  | Summer 2026 - ongoing | Professional learning agendas, survey results |  | Staff time for training |  | Title II, Title 1, SIG funds |
| Pilot revised master schedule in selected grade levels/high-need classrooms | Principal | August 2026 – ongoing (September 2027) |  | Schedule audits, walkthrough/observation data | Walkthrough and observation data; schedule audit for check ins |  | N/A |  | N/A |
| Implement revised master schedule schoolwide | Principal | August 2026 |  | Walkthrough, observations weekly | Schedule audit through walkthrough/observation data |  | N/A |  | N/A |
| Monitor literacy outcomes and subgroup performance data | Principal/Chief Academic Officer | May 2026 – ongoing |  | ILT Agenda notes, accountability data checks monthly | Division data and accountability files; academic review |  | Staff planning time, pay beyond contract hours |  | SIG Funds |
| Refine and sustain master schedule based on data and feedback | Principal | October 2026 - ongoing |  | Schedule audits, observation/walkthrough data | Surveys, schedule audits |  | Created surveys, planning time |  | SIG Funds |

| Addressing Resource Inequities Plan |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3-Year Goal Statement Include the goal statement completed as part of the Resource Inequity Review process. |  |  | By 2028, Preston Park will implement and sustain a coherent, job-embedded professional learning system that is clearly aligned to school and district instructional priorities while also providing teachers with guided autonomy to address instructional challenges within their local context. Professional learning will be embedded within the instructional cycle, supported by collaborative planning, coaching, and feedback, and monitored through clear measures of implementation and impact. As a result, teachers will consistently apply evidence based instructional practices aligned to district goals while exercising professional judgment to meet student needs, leading to improved instructional coherence, stronger instructional practice, and increased student achievement across content areas and student groups. |  |  |  |  |  |  |
| Measurable Objectives Define objectives that support accomplishing the goal. |  |  | Measurable Objective Year 1 |  |  | Measurable Objective Year 2 |  | Measurable Objective Year 3 |  |
|  |  |  | By July 2026 will design and pilot thematic job embedded professional development where 50% of focus will be a mixture of evidence based practices, and teacher practice in local context through professional learning communities and intentional coaching and/or consultation for 100% of teachers. |  |  | By June 2027 will fully implement job embedded professional development where 75% of teachers attend and 50% of focus will be evidence based, teacher led, and improved practice. |  | By June 2028 will sustain job embedded professional development where 100% of teachers are leading job embedded professional development using evidence based practices, collaborative structures, and engaged in a plan-do-study-act cycle for student achievement gains. |  |
| Strategy Describe the strategy and the rationale for selection. |  |  | Preston Park Elementary will design, implement, and then sustain job embedded professional development that is clearly aligned to school and district instructional priorities. This strategy focuses on improving teacher learning, reflection, collaboration, and efficacy. |  |  |  |  |  |  |
| Intended Outcomes Describe how student outcomes will improve as a result implementing the strategy. |  |  | - Teachers will consistently apply evidence based instructional practices aligned to district goals while exercising professional judgment to meet student needs, - Leading to improved instructional coherence, stronger instructional practice, and increased student achievement across content areas and student groups. - Observable student engagement through investing and driving (asking appropriate questions, setting goals, valuing the learning through reflection, using academic language with the teacher) - Student performance and data will show consistent growth across all subgroups, subjects, and cohorts |  |  |  |  |  |  |
| Lead person (Who is responsible for ensuring the work gets done?) |  |  | Principal |  |  |  |  |  |  |
| Team Members (Who are responsible for doing the work?) |  |  | Assistant Principal(s), Targeted School Improvement Mentor, Instructional Coach, Reading Specialist(s), Classroom Teachers |  |  |  |  |  |  |
| Action Step (What will be accomplished?) List the specific, sequenced steps required to complete the activity. | Process Owner (Who is responsible for ensuring the action step is complete?) Identify a single, accountability lead. | Time Frame (How long will it take?) Identify the start and end dates for each action step, including any key milestones. |  | Progress Checks (How will the team monitor progress?) Define key dates to review process, make adjustments, and confirm the work remains on track. | Measures of Success (How will the team know if the action step is complete?) Define clear, observable indicators of completion. |  | Cost Elements (What resources are needed to complete the action step?) |  | Funding Source (Where will the money come from?) |
| Conduct needs assessment to identify teacher learning priorities aligned to district goals | Principal | Fall 2026 |  | PLC discussions; survey analysis; leadership team reviews | Identified PD priorities aligned to instructional focus areas |  | Staff time |  | Title I / Local |
| Design job-embedded professional learning framework (PLC structure, coaching cycles, focus areas) | Targeted School Improvement Mentor | Summer 2026 |  | Draft framework reviews; feedback loops | Completed professional learning plan aligned to goals |  | Staff time |  | Local |
| Provide initial training on evidence-based practices and collaborative structures | Principal | Winter–Spring 2026 |  | PD attendance; feedback surveys; observation data | Teachers demonstrate understanding of key practices |  | Materials, stipends |  | Title II |
| Implement coaching cycles and PLC structures to support teacher practice | Instructional Coach | 2026–2027 school year |  | Coaching logs; PLC agendas; walkthroughs | 100% of teachers engaged in coaching/PLC cycles |  | Staff time |  | Title II |
| Pilot job-embedded professional learning model with ongoing coaching and reflection | Principal | Spring 2027 |  | Reflection protocols; teacher feedback; student engagement data | 50% of PD reflects application in local context; improved teacher practice observed |  | Staff time |  | Local |
| Expand implementation to full staff with consistent coaching and PLC expectations | Instructional Coach | 2026–2027 school year |  | Quarterly reviews; walkthrough data; PLC documentation | 75% of teachers regularly participate in job-embedded PD |  | Staff time |  | Local |
| Support teacher-led professional learning and facilitate shared leadership | Targeted School Improvement Mentor | 2026–2028 |  | PLC facilitation logs; peer observations | Increase in teacher-led PD sessions and collaboration quality |  | Stipends (if applicable) |  | Title II |
| Monitor instructional practices and student outcomes across classrooms | Principal | Quarterly 2026–2028 |  | Data meetings; trend analysis reviews | Improvement in student performance and reduction in disruptions |  | Data tools |  | Local |
| Sustain continuous improvement through plan-do-study-act cycles | Principal | 2027–2028 |  | Annual evaluation; stakeholder feedback | Monitoring system is embedded and consistently implemented with fidelity |  | Staff time |  | Local |

| Addressing Resource Inequities Plan |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3-Year Goal Statement Include the goal statement completed as part of the Resource Inequity Review process. |  |  | By the year 2028, Preston Park Elementary will implement and sustain clear, consistent, and transparent monitoring routines that systematically identify, act upon, and track progress toward school‑wide goals aligned to district priorities. These routines will include defined data review cycles, shared implementation indicators, and regular feedback loops that guide instructional, staffing, and climate decisions. As a result, school leadership and instructional teams will use timely evidence to adjust practice, ensure fidelity of implementation, and maintain focus on high‑leverage goals, leading to improved instructional coherence, stronger adult accountability, and sustained improvements in student outcomes. |  |  |  |  |  |  |
| Measurable Objectives Define objectives that support accomplishing the goal. |  |  | Measurable Objective Year 1 |  |  | Measurable Objective Year 2 |  | Measurable Objective Year 3 |  |
|  |  |  | By July 2026 Preston Park will continue to implement clear, consistent, and transparent monitoring routines such that: - Monitoring systems are implemented at a 100% Level 1 (foundational level) - Data review cycles and expectations are clearly defined and communicated - Initial indicators of implementation are established and used to guide practice |  |  | By June 2027 Preston Park will strengthen implementation of monitoring routines such that: - Monitoring systems are implemented at a 100% Level 2 (developing level) - Consistent data review cycles and feedback loops are used across teams - Monitoring informs instructional adjustments and staff actions |  | By June 2028 will sustain clear, consistent, and By June 2028, Preston Park will sustain monitoring routines such that: - Monitoring systems are implemented at a 100% Level 3 (sustained level) - Data-driven decision making and feedback loops are embedded in all practices - Monitoring results in consistent improvements in instruction, climate, and student outcomes |  |
| Strategy Describe the strategy and the rationale for selection. |  |  | Through guided language acquisition design, instructional leaders and teachers will improve implementation of academic language instruction through grade level content for Emerging Bilinguals and English Learners. The rationale for this intentional strategy is for the renewed commitment to high expectations and high standards for all students. The results for students have continued gains in standardized test scores as well as renewed involvement in a classroom that is, not only student-centered, but fosters a sense of identity and voice |  |  |  |  |  |  |
| Intended Outcomes Describe how student outcomes will improve as a result implementing the strategy. |  |  | - Instructional settings and classrooms to adjust practices for defined usage of strategies; - Ensure fidelity of implementation across all content areas behaviorally; - Maintain focus on high‑leverage goals leading to improved instructional coherence - Stronger adult accountability within monitoring, observation and evaluation - Sustained improvements in student outcomes through monitoring of both student achievement data and reduction in infractions and disruptions |  |  |  |  |  |  |
| Lead person (Who is responsible for ensuring the work gets done?) |  |  | Principal |  |  |  |  |  |  |
| Team Members (Who are responsible for doing the work?) |  |  | Assistant Principal(s), Targeted School Improvement Mentor, Instructional Coach, Reading Specialist(s), Classroom Teachers |  |  |  |  |  |  |
| Action Step (What will be accomplished?) List the specific, sequenced steps required to complete the activity. | Process Owner (Who is responsible for ensuring the action step is complete?) Identify a single, accountability lead. | Time Frame (How long will it take?) Identify the start and end dates for each action step, including any key milestones. |  | Progress Checks (How will the team monitor progress?) Define key dates to review process, make adjustments, and confirm the work remains on track. | Measures of Success (How will the team know if the action step is complete?) Define clear, observable indicators of completion. |  | Cost Elements (What resources are needed to complete the action step?) |  | Funding Source (Where will the money come from?) |
| Establish clear monitoring framework including data cycles, expectations, and roles | Principal / ILT | Fall 2026 |  | Leadership meetings; framework review checkpoints | Documented monitoring system with defined roles and expectations |  | Staff time |  | Local |
| Identify and define key indicators for instructional practice, student outcomes, and climate | Principal / Data Team | Fall 2026 |  | Indicator review sessions; team feedback | Shared set of measurable indicators used across teams |  | Staff time |  | Local |
| Implement structured data review cycles (PLC, leadership, and whole-school) | AP / Coaches | 2026–2027 school year |  | PLC agendas; data meeting notes | Regular data cycles occurring with documented discussions |  | Staff time |  | Local |
| Provide training on data use, monitoring tools, and instructional adjustments | Instructional Coaches / TSIM | Winter 2026–Spring 2027 |  | PD attendance; feedback; walkthroughs | Staff demonstrate ability to use data for instructional decisions |  | PD materials, stipends |  | Title II |
| Integrate guided language acquisition strategies into monitoring and instructional reviews | EL Staff / Coaches | 2026–2027 school year |  | Observation data; lesson plan reviews | Evidence of academic language strategies in classrooms |  | Staff time |  | Title III / Local |
| Use monitoring routines to guide instructional and behavioral adjustments | Principal / ILT | 2026–2027 school year |  | Quarterly reviews; walkthrough trends | Data-driven adjustments evident in instruction and climate practices |  | Staff time |  | Local |
| Strengthen feedback loops between leadership and teachers (coaching, observations, follow-up) | Principal | 2026–2028 |  | Observation feedback cycles; coaching logs | Increased alignment between feedback and classroom practices |  | Staff time |  | Title II |
| Monitor student achievement and behavior trends across subgroups | Principal | Quarterly 2026–2028 |  | Data meetings; trend analysis reviews | Improvement in student performance and reduction in disruptions |  | Data tools |  | Local |
| Refine and sustain monitoring routines with continuous improvement cycles | Principal / ILT | 2027–2028 |  | Annual evaluation; stakeholder feedback | Monitoring system is embedded and consistently implemented with fidelity |  | Staff time |  | Local |

Assurances

## Assurance of Review and Approval

School Year: 2026-2027

Division Name: Roanoke City Public Schools

Division-Level Team Lead Name: Archie Freeman

Division-Level Team Lead Email: afreeman@rcps.info

School Name: Preston Park Elementary School

Principal Name: Tracey Hoffman

Principal Email: thoffman@rcps.info

School Performance Category: Needs Intensive Support

School Federal Designation: Comprehensive Support and Improvement - Low Performing

For Comprehensive Support and Improvement Schools, the Multi-year School Support Plan must be written by the school division for the school and include four evidence-based Interventions. The proposed plan must be approved by the principal and division, reviewed by the local school board, and submitted to the Virginia Department of Education (the Department) by the Division Superintendent for final approval. The Virginia Department of Education will review the plan and may request revisions before approving the plan. The Department-approved plan must be published on the division website and the school website. The Multi-year School Support Plan will be incorporated as a component of the school's comprehensive, unified, long-range plan. (8VAC20-132-280(C)(1)) (ESEA Section 1111(d)(1)(B)(v)).

For Targeted Support and Improvement and Additional Targeted Support and Improvement schools, the Multi-year School Support Plan must be written by the school and include two evidence-based Interventions. The proposed plan must be approved by school division and the local school board. The approved plan must be published on the division website and the school website. The Multi-year School Support Plan will be incorporated as a component of the school's comprehensive, unified, long-range plan. (8VAC20-132-280(B)) (ESEA Section 1111(d)(2)(B)(iii)).

By signing below, I certify that I have thoroughly reviewed the Multi-year School Support Plan for the federally identified school named in this document. I affirm that the plan:

- Aligns with federal and state requirements for school improvement;

- Addresses the needs identified through a school needs assessment;

- Includes the minimum number of required evidence-based interventions;

- Reflects stakeholder input and collaboration; and

- Establishes clear goals, timelines, and progress monitoring processes.

I approve the contents of this plan and commit to supporting its implementation with fidelity to ensure improved outcomes for all students.

| Principal Name |  | Principal Signature |  | Date Approved |
| --- | --- | --- | --- | --- |
| Division-Level Lead Name |  | Division-Level Lead Signature |  | Date Approved |
| Division Superintendent Name |  | Division Superintendent Signature |  | Date Approved |
|  |  |  |  | Date Reviewed/Approved per School Board Minutes |

## Additional Support and Next Steps

This plan serves as the strategic roadmap for improvement and is included in the suite of resources provided by the Office of School Improvement. Supports are also available on the Road to Readiness webpage.