### Division and School Information

#### Table 2: Division and School Information

| Information Needed | Enter Information Below |
| --- | --- |
| School Year | 2025-2026 |
| Division Name | Roanoke City Public Schools |
| Division Superintendent | Verletta White |
| School Name | Westside Elementary |
| Grades Served | PK-5 |
| Principal Name | Kristen English |
| Principal Email | kenglish@rcps.info |
| Division Multi-year School Support Plan Lead Name and Title | Kevin G. Bowman, Supervisor of School Improvement |
| Division Multi-year School Support Plan Lead Email | kevinbowman@rcps.info |

### Stakeholder Engagement

Developing the plan with stakeholders is required and includes teachers, school leaders, community partners, parents, students, and representatives from business, higher education, or the military. Actively involving stakeholders supports purposeful planning, builds shared ownership, and helps translate the plan from intent to action, leading to improved student outcomes.

#### Table 3: Stakeholder engagement

Identify the stakeholder group represented, name, email department/office/organization, and title for each stakeholder. Add or remove rows as necessary.

| Stakeholder Representation | Name | Email | Organization, Department, or Office | Title |
| --- | --- | --- | --- | --- |
| School | Dr. Kristen English | kenglish@rcps.info | Westside | Principal |
| School | Krystal Paitsel | kpaitsel@rcps.info | Westside | Assistant Principal |
| School | Dr. Poldi Moreno | pmoreno@rcps.info | Westside | Assistant Principal |
| School | Alisha Perkins | aperkins@rcps.info | Instruction & Administration | Targeted School Improvement Mentor |
| School | Maryann Mitzel | mmitzel@rcps.info | Westside | Instructional Coach |
| School | Brian Epperly | bepperly@rcps.info | Westside | Dean of Students |
| School | Stephanie Finch | sfinch@rcps.info | Westside | Reading Specialist |
| School | Kara Garrett | kgarrett@rcps.info | Westside | Reading Specialist |
| School | Sarah Rybitski | srybitski@rcps.info | Westside | Reading Specialist |
| Division | Kevin Bowman | kbowman@rcps.info | Instruction & Administration | Supervisor of Targeted School Improvement |
| Division | Dr. Laurie Wimbush | lwimbush@rcps.info | Instruction & Administration | Assistant Superintendent of Instruction & School Improvement |
| Division | Rachel Floyd | rafloyd@rcps.info | Academics & Accountability | Supervisor of Reading Improvement & Reading Specialists |

Multi-year School Support Plan

| Multi-year School Support Plan Reading |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3-Year Goal Statement Include the goal statement completed as part of the needs assessment process. |  |  | Increase reading proficiency and growth for all students by implementing explicit, systematic reading instruction, strengthening co‑teaching and intervention practices, and ensuring consistent use of high‑quality instructional materials. By 2028, all student groups will demonstrate sustained improvements on the Reading SOL, with significant gains for english language learners, and students with disabilities. |  |  |  |  |  |  |
| School Performance and Support Framework Alignment Select indicator that the goal addresses. |  |  | Reading Growth |  |  |  |  |  |  |
| Measurable Objectives Define objectives that support accomplishing the goal. |  |  | Measurable Objective Year 1 |  | Measurable Objective Year 2 |  |  | Measurable Objective Year 3 |  |
|  |  |  | Increase overall Reading SOL pass rate to 80% and not be federally identified in subgroups. Ensure 100% of teachers implement division‑approved literacy materials and evidence‑based reading routines (decoding, morphology, comprehension routines) as documented through walkthroughs and lesson plan reviews. |  | Increase Reading SOL pass rates by an additional 5–7% across all student groups. Improve Reading Benchmark averages to 65% or higher. Strengthen alignment between Tier 1 instruction and intervention using data from VALLSS, MAP, and Lexia. |  |  | Demonstrate cumulative growth sufficient to close gaps and sustain proficiency increases across all student groups. Increase Reading Benchmark averages to 70% or higher. Demonstrate full fidelity to foundational skills routines, comprehension-building practices, and co‑teaching structures across all classrooms. |  |
| Evidence-Based Strategy Describe the evidence-based strategy and the rationale for selection. Identify evidence tier. |  |  | Foundational Skills (K–3) Explicit instruction in decoding, phonics, word analysis, and reading fluently through systematic routines and aligned materials. Upper Elementary Comprehension (Grades 4–5) Daily use of comprehension‑building practices, including: Building world and word knowledge Teaching students how to ask and answer text-dependent questions Using routines to determine the gist Teaching students to monitor their comprehension Rationale: Students at Westside require consistent, explicit reading instruction that addresses decoding, vocabulary, and comprehension gaps. High-quality instructional materials and routines (e.g., morphology, questioning, gist routines) directly support students’ ability to understand grade-level text and demonstrate proficiency on SOLs and MAP assessments. |  |  |  |  |  |  |
| Intended Outcomes Describe how student outcomes will improve as a result implementing the evidence-based strategy. |  |  | Improved decoding, fluency, and word recognition for early readers. Increased vocabulary, background knowledge, and comprehension for grades 3–5. Stronger alignment between Tier 1 instruction, intervention, and assessment data. Increased Reading SOL proficiency and MAP growth across all subgroups. Reduced performance gaps for students with disabilities and English language learners. |  |  |  |  |  |  |
| Lead person (Who is responsible for ensuring the work gets done?) |  |  | Principal (Kristen English) |  |  |  |  |  |  |
| Team Members (Who are responsible for doing the work?) |  |  | Assistant Principal, School Improvement Mentor, Instructional Coach, Dean of Students, Literacy Coach, Classroom Teachers, SPED Teachers, EL Teachers |  |  |  |  |  |  |
| Action Step (What will be accomplished?) List the specific, sequenced steps required to complete the activity. | Process Owner (Who is responsible for ensuring the action step is complete?) Identify a single, accountability lead. | Time Frame (How long will it take?) Identify the start and end dates for each action step, including any key milestones. |  | Progress Checks (How will the team monitor progress?) Define key dates to review process, make adjustments, and confirm the work remains on track. |  | Measures of Success (How will the team know if the action step is complete?) Define clear, observable indicators of completion. | Cost Elements (What resources are needed to complete the action step?) |  | Funding Source (Where will the money come from?) |
| Strengthen Tier 1 Lesson Planning and Alignment Design and monitor lesson plans and professional learning team structures to ensure instruction aligns with the Virginia SOLs and Curriculum Framework. | Administration, School Improvement Mentor, Instructional Coach, Dean of Students | August 2025 – May 2026 |  | Weekly Lesson plan reviews, walkthrough feedback |  | Lesson plans and instruction reflect accurate SOL alignment and use of high-quality instructional materials | None |  | N/A |
| Facilitate and Monitor PLCs, Including Monthly Literacy PLCs Provide structures for teachers to analyze reading data, plan instruction, and build capacity around alignment to the standards. | Administration, School Improvement Mentor, Instructional Coach, Dean of Students, Literacy Coach | August 2025 – May 2026 |  | PLC agendas; data discussions; regrouping documentation |  | More targeted instruction and increased student performance on benchmarks and MAP | None |  | N/A |
| Provide Instructional Feedback Cycles Use the observation process to ensure that instruction reflects explicit foundational skills (K–3) and comprehension routines (3–5) aligned with HQIM. | Administration, School Improvement Mentor, Instructional Coach, Dean of Students | August 2025 – May 2026 |  | Observation/feedback logs |  | Documented increased fidelity to evidence-based literacy practices | None |  | N/A |
| Professional Development on the Science of Reading Provide PD to build teacher capacity in foundational literacy, morphology, fluency, and comprehension-building techniques. | Administration, Division Literacy Coaches, School Improvement Mentor, Instructional Coach, Dean of Students | August 2025 – May 2026 |  | PD attendance, coaching cycles, application in classrooms |  | Improved instructional quality and student outcomes on literacy assessments | None |  | SIG |
| Data-Driven Differentiation and Grouping Use VALLSS, MAP, Lexia, Imagine Learning, UFLI, and Reading Playground data to regroup students and adjust instruction. | Administration, School Improvement Mentor, Instructional Coach, Dean of Students, SPED Teachers, EL Teachers | September 2025 – May 2026 |  | Grouping schedules, progress monitoring charts |  | Improved fluency, comprehension, and benchmark outcomes | None |  | N/A |
| Implement High-Leverage Instructional Practices Teachers will implement routines such as explicit vocabulary instruction, structured reading protocols, morphology instruction, and student discourse to improve comprehension and analysis. | Administration, School Improvement Mentor, Instructional Coach, Dean of Students | August 2025 – May 2026 |  | Walkthrough data; lesson plan checks |  | Increased student engagement, comprehension, and reading performance | None |  | SIG |
| EL Co-teaching Cohort | Administration, School Improvement Mentor, Instructional Coach, Dean of Students | March 2026 – October 2026 |  | Walkthroughs, lesson plan checks, cohort meetings |  | Improved outcomes for the EL subgroup on multiple data points such as class grades, class assignments, and assessments. | None |  | N/A |
| SOAR afterschool program | Administration, Dean of Students | February 2026 – April 2026 |  | Walkthroughs, lesson plan checks |  | Improved instructional quality and student outcomes on literacy assessments | None |  | SIG |

| Multi-year School Support Plan Math |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3-Year Goal Statement Include the goal statement completed as part of the needs assessment process. |  |  | Increase the percentage of students passing the VA Math SOL to meet or surpass grade-level expectations by implementing systematic instruction, concrete–representational–abstract (CRA) strategies, and word-problem routines. By 2028, the school will demonstrate sustained improvement in math growth and proficiency for all subgroups, with especially strong gains for students with disabilities and English language learners. |  |  |  |  |  |  |
| School Performance and Support Framework Alignment Select indicator that the goal addresses. |  |  | Math Growth |  |  |  |  |  |  |
| Measurable Objectives Define objectives that support accomplishing the goal. |  |  | Measurable Objective Year 1 |  | Measurable Objective Year 2 |  |  | Measurable Objective Year 3 |  |
|  |  |  | Increase overall Math SOL pass rate to 80% and not be federally identified in subgroups. Ensure 100% of K–5 teachers implement concrete, pictorial, and abstract (CRA) modeling during math instruction. |  | Increase math proficiency rates by an additional 5–7% across all subgroups. Increase the quality of Tier 1 instruction through accurate alignment to content and cognition as documented through walkthrough tools. Improve interim benchmark averages to 65% or higher. |  |  | Achieve and maintain proficiency levels at or above state expectations, with at least a 30% cumulative increase in overall math performance from baseline. Demonstrate consistent, schoolwide implementation of CRA modeling and systematic instruction during Tier 1 and intervention. |  |
| Evidence-Based Strategy Describe the evidence-based strategy and the rationale for selection. Identify evidence tier. |  |  | Systematic instruction to build deep conceptual understanding in small-group and whole-group settings. Concrete, pictorial, and abstract representations to support concept development and procedural fluency. Deliberate instruction on word problems to strengthen comprehension and multi-step reasoning. Rationale: Math data at Westside shows that students struggle with multi-step problem solving, conceptual understanding, and use of models. CRA modeling, systematic instruction, and explicit word-problem routines directly match these needs and are research-based practices with strong evidence of effectiveness. |  |  |  |  |  |  |
| Intended Outcomes Describe how student outcomes will improve as a result implementing the evidence-based strategy. |  |  | Students will develop stronger conceptual understanding and number sense through systematic instruction. Students will accurately use visual representations (number lines, models, arrays, bar models) to solve problems. Students will demonstrate increased independence and accuracy with multi-step problems. Benchmark, MAP, VKRP, and SOL performance will increase across all grades and subgroups. Students with disabilities will show significant gains in growth and proficiency. |  |  |  |  |  |  |
| Lead person (Who is responsible for ensuring the work gets done?) |  |  | Principal (Kristen English) |  |  |  |  |  |  |
| Team Members (Who are responsible for doing the work?) |  |  | Assistant Principal, School Improvement Mentor, Instructional Coach, Division Math Coach, Dean of Students, Classroom Teachers, SPED Teachers, All-In Tutors |  |  |  |  |  |  |
| Action Step (What will be accomplished?) List the specific, sequenced steps required to complete the activity. | Process Owner (Who is responsible for ensuring the action step is complete?) Identify a single, accountability lead. | Time Frame (How long will it take?) Identify the start and end dates for each action step, including any key milestones. |  | Progress Checks (How will the team monitor progress?) Define key dates to review process, make adjustments, and confirm the work remains on track. |  | Measures of Success (How will the team know if the action step is complete?) Define clear, observable indicators of completion. | Cost Elements (What resources are needed to complete the action step?) |  | Funding Source (Where will the money come from?) |
| Curriculum Alignment Training Provide training on aligning written, taught, and tested curriculum using the Virginia Standards of Learning and Curriculum Framework, ensuring alignment in both content and cognition. | Administration, Division Math Coach, School Improvement Mentor, Instructional Coach, Dean of Students | August 2025 – May 2026 |  | Lesson plan reviews, walkthrough tools, PD attendance |  | Increased alignment between lesson plans and observed instruction | None |  | N/A |
| Conduct Instructional Walkthroughs for Math Fidelity Conduct walkthroughs and provide feedback to ensure systematic instruction, CRA modeling, and word-problem routines are implemented consistently. | Administration, School Improvement Mentor, Instructional Coach, Dean of Students | August 2025 – May 2026 |  | Weekly Walkthrough data, feedback cycles |  | Increased fidelity to evidence-based math practices | None |  | Local |
| Provide Systematic Small-Group Instruction for Students Below Benchmark Use Zearn, Hand2Mind, VKRP, and other resources to address conceptual gaps, provide targeted practice, and strengthen foundational skills. | Administration, School Improvement Mentor, Instructional Coach, All-In Tutors, Dean of Students | August 2025 – May 2026 |  | Monthly review of intervention plans and progress logs in PLCs; Small-group logs, VKRP and MAP growth indicators |  | Increased performance on benchmarks and MAP; documented growth for identified students | None |  | SIG |
| Implement and Monitor Math Interventions Include intervention staff in planning, track specific intervention strategies, and evaluate student progress to determine which interventions yield positive results. | Administration, School Improvement Mentor, Instructional Coach, Dean of Students | August 2025 – May 2026 |  | Intervention logs, data meetings |  | Increased rates of students meeting benchmark expectations | Assessment tools |  | N/A |
| Facilitate Math PLCs Monitor PLC meetings to ensure teams are analyzing math assessment data, reviewing student work, and planning instruction aligned to standards and cognitive demand. | Administration, School Improvement Mentor, Instructional Coach, Dean of Students | August 2025 – May 2026 |  | PLC agendas and notes |  | Improved lesson alignment; targeted student groupings | None |  | SIG |
| Data-Informed Differentiated Instruction Use assessment data (MAP, VKRP, Benchmarks, Snapshots) to regroup students for differentiated instruction that meets their specific needs. | Administration, School Improvement Mentor, Instructional Coach, Dean of Students | September 2025 – May 2026 |  | Grouping logs; benchmark summaries; MAP growth reports |  | Improved mastery levels across all subgroups | None |  | N/A |
| Implement High-Leverage Instructional Practices During Math Instruction Provide explicit modeling, guided practice, discourse-driven problem solving, and structured routines to strengthen conceptual understanding. | Administration, School Improvement Mentor, Instructional Coach, Dean of Students | August 2025 – May 2026 |  | Walkthrough data; observation notes |  | Increased student engagement and demonstration of mathematical reasoning | None |  | N/A |
| EL Co-teaching Cohort | Administration, School Improvement Mentor, Instructional Coach, Dean of Students | March 2026 – October 2026 |  | Walkthroughs, lesson plan checks, cohort meetings |  | Improved outcomes for the EL subgroup on multiple data points such as class grades, class assignments, and assessments. | None |  | N/A |
| SOAR afterschool program | Administration, Dean of Students | February 2026 – April 2026 |  | Walkthroughs, lesson plan checks |  | Improved instructional quality and student outcomes on math assessments | None |  | SIG |

Assurances

## Assurance of Review and Approval

School Year: 2025-2026

Division Name: Roanoke City Public Schools

Division-Level Team Lead Name: Archie Freeman III

Division-Level Team Lead Email: afreeman@rcps.info

School Name: Westside Elementary

Principal Name: Kristen English

Principal Email: kenglish@rcps.info

School Performance Category: Choose an item.Off Track

School Federal Designation: Choose an item.Targeted Support and Improvement

For Comprehensive Support and Improvement Schools, the Multi-year School Support Plan must be written by the school division for the school and include four evidence-based Interventions. The proposed plan must be approved by the principal and division, reviewed by the local school board, and submitted to the Virginia Department of Education (the Department) by the Division Superintendent for final approval. The Virginia Department of Education will review the plan and may request revisions before approving the plan. The Department-approved plan must be published on the division website and the school website. The Multi-year School Support Plan will be incorporated as a component of the school's comprehensive, unified, long-range plan. (8VAC20-132-280(C)(1)) (ESEA Section 1111(d)(1)(B)(v)).

For Targeted Support and Improvement and Additional Targeted Support and Improvement schools, the Multi-year School Support Plan must be written by the school and include two evidence-based Interventions. The proposed plan must be approved by school division and the local school board. The approved plan must be published on the division website and the school website. The Multi-year School Support Plan will be incorporated as a component of the school's comprehensive, unified, long-range plan. (8VAC20-132-280(B)) (ESEA Section 1111(d)(2)(B)(iii)).

By signing below, I certify that I have thoroughly reviewed the Multi-year School Support Plan for the federally identified school named in this document. I affirm that the plan:

- Aligns with federal and state requirements for school improvement;

- Addresses the needs identified through a school needs assessment;

- Includes the minimum number of required evidence-based interventions;

- Reflects stakeholder input and collaboration; and

- Establishes clear goals, timelines, and progress monitoring processes.

I approve the contents of this plan and commit to supporting its implementation with fidelity to ensure improved outcomes for all students.

| Principal Name |  | Principal Signature |  | Date Approved |
| --- | --- | --- | --- | --- |
| Division-Level Lead Name |  | Division-Level Lead Signature |  | Date Approved |
| Division Superintendent Name |  | Division Superintendent Signature |  | Date Approved |
|  |  |  |  | Date Reviewed/Approved per School Board Minutes |