## CMAR Proposal Summary Sheet
| CMAR Proposal for: Dallas Independent School District Project : W. W. Samuell H. S. - New Construction |  | CMAR Business Name: XXXXXXXXXXXXXXXX
| Bid Breakdown of Total Expected CMAR Construction Costs | CMAR Proposed Amounts | Instructions for Completing RFP Response with Estimated NTE Amounts | Memo Only % of Total CCL | Memo Cost of Work NIC Liability Insurance and Fee | Memo Only: Liability insurance as a % of Cost Of Work NIC Fee and Liability Insurance
Line 1.A | CMAR is to provide a Proposal Total Lump to Provide all of the Preconstruction services and GMP Development Services necessary to deliver this project. The Approved Amount for Preconstruction Services will be Issued as GMP Amendment #1 per the DISD RFP Document. The amount for Preconstruction Services will need to cover the development and finalization of all required GMP Proposals. | 0 | Proposer is to use the Tab 1.A to provide a detailed breakdown of their proposed lump sum charges for the preconstruction deliverables detailed in Article 3.1 and Article 3.2 of the A133 agreement; as well as the preconstruction services detailed in the DISD RFP document. Note: This amount will be included in competitive price determination of CMAR Best Value.
Line 1.B | Total Proposed Estimated Not-to-Exceed Cost for all Reimbursable CMAR Staff and any related consultants expected to perform work on the project during the project Construction Phase. | 0 | Proposer is to use Tab 1.B to estimate their proposed total NTE for all anticipated CM staff and any necessary consultants based on the anticipated schedule of the project as it was known at the time this RFP is submitted. The amount entered here will be the total of the detailed estimate calculated in Tab 1.B of this workbook. Note: Amounts entered are expected to only reflect reimbursable costs allowable per the Owner A133. NOTE: All amounts entered will be subject to Owner review and any excessive costs or costs not allowed by the A133 will be disallowed when the NTE amount is negotiated with the Best Value Proposer. No adjustments to the Proposer's Fee will be permitted. Note: This amount will be included in competitive price determination of CMAR Best Value.
Line 1.C | Total Proposed Estimated Not-to-Exceed Cost for Non-Staff General Conditions, General Requirements and Post Construction from Detailed Estimate Tab 1.C | 0 | Proposer is to use Tab 1.C to estimate their proposed total NTE for all anticipated CM staff and any necessary consultants based on the anticipated schedule of the project as it was known at the time this RFP is submitted. The amount entered here will be the total of the detailed estimate calculated in Tab 1.B of this workbook. Note: Amounts entered are expected to only reflect reimbursable costs allowable per the Owner A133. NOTE: All amounts entered will be subject to Owner review and any excessive costs or costs not allowed by the A133 will be disallowed when the NTE amount is negotiated with the Best Value Proposer. No adjustments to the Proposer's Fee will be permitted. Note: This amount will be included in competitive price determination of CMAR Best Value.
Line 2 | Total Estimated Actual Cost of Providing Builder's Risk Insurance Required by the A133 Exhibit B as modified by Owner. | 0 | Proposer is to enter the total amount they expect to pay for conventionally required Builder's Risk insurance over the life of the job. The amount to be reimbursed will be the actual invoiced cost to the CM net of any return premium that would be received if there is a savings at the end of the job. Note: This amount will be used for determining Best Value and will be considered a maximum DISD will reimburse for the required Builder's Risk Policy. |  |  |  | D
Line 3 | Total Estimated Actual Cost of Providing CM's Performance and Payment Bond Required by the A133 Exhibit B as modified by Owner. Note: For this project the maximum to be considered reimbursable for the Bond for the Construction Phase of the project will be limited to .7% of the approved GMP's (not Including any amount approved for Preconstruction Phase and GMP Development Phase Services.) The billable amount for CM P&P bonds will be the actual bond invoice costs net of any actual bond dividend or return premium received to be received.) | 0 | Proposer is to enter the total amount they expect to pay for conventionally required Builder's Risk insurance over the life of the job. The amount to be reimbursed will be the actual invoiced cost to the CM net of any return premium that would be received if there is a savings at the end of the job. Note: This amount will be used for determining Best Value and will be considered a maximum DISD will reimburse for the required Builder's Risk Policy.
Line 4 | Total Estimated Actual Cost of Providing All Conventionally Procured Liability Insurance Required in accordance with the A133 Exhibit B as modified by Owner. (Note: Per the A133 Reimbursement for all Required Liability insurance will be limited to .6% of All Reimbursable Cost of Work but not including the Reimbursable cost of Liability Insurance.) | 0 | Proposer is to enter the total amount they expect to be reimbursed for conventionally procured liability insurance over the life of the job subject to the contractual limit not-to-exceed the A133 contractual limit of .6% of the estimated allowable Cost of Work not including the allowable costs of liability insurance, and the CM Fee. Note: If the CM's actual cost of providing all of the contractually required liability insurance is expected to exceed the contractual limit; the balance of the CM's liability insurance cost will have to be considered covered by their proposed CM Fee. Note: This amount will be used for determining Best Value and will be considered a maximum DISD will reimburse for the required Builder's Risk Policy. |  |  | #REF!
Line 6 | Total Estimated Reimbursable Cost of Work plus fee Including Contingency. This calculated is the Maximum Construction Phase Funds Available after deducting Preconstruction and CM Fee from the total Available CCL/Project Maximum Budget | 150000000 | Note: This amount is automatically calculated based on the values in Line 1.A, Line 8 and Line 9.
Line 7 | CM Fee in the contract will be Expressed a % of Reimbursable Cost of Work Not Including Preconstruction and not including CM Fee. | 0 | This Fee amount is automatically calculated based on % entered into Line 9. | 0%
| Total Budget Available for GMPs for Construction Phase Costs Plus CM Fee | 150000000 | The Amount will be automatically calculated after deducting Proposed Preconstruction Lump Sum Fee from Line 1.A
Line 8 | Total Current Amount Available Budget for the CMAR Contract (Construction Cost Limitation or CCL) | 150000000 | This is the Total Project CMAR Contract Budget as documented in the DISD RFP for this Project.
Line 9 | Memo Only: CM Proposed Percentage Fee will be Calculated on Total Actual Reimbursable Cost of Work per the A133 Agreement subject to the overall limitation of the Agreed Upon Guaranteed Maximum Price. Preconstruction Services will be the Agreed Upon Lump Sum and no CM Fee or insurance will be paid on the Preconstruction Services Fee. | 0% | CMAR is to enter their competitive bid CMAR Fee % in the box to the left in this Line 9. | 100%
Line 10 | Note: Owner will reimburse the CM for the actual cost of performance and payment bonds requested to be provided by Trade Contractors. If subcontractors are to be bonded, the trade contractors will be required to provide an invoice from their surety company to be eligible for reimbursement for the actual cost of purchasing any requested performance and payment bonds.
Line 11 | Note: , Subcontractor Default Insurance (SDI) will be reimbursed to CM in lieu of Trade Contractor Performance and Payment Bonds. The maximum percentage to be paid to the CM for SDI will be 1% of enrolled trade contracts. See the applicable provisions of the A133 for more details.
Line 12.A | Note: Providing insurance conventionally is required to be quoted to be responsive to this RFP. However, Owner may consider the use of CCIP as an alternate to providing all required liability insurance and worker's compensation insurance conventionally by the CM and all levels of eligible Trade Contractors. Owner may consider using an approved "Contractor Controlled Insurance Program" (CCIP); however, use of CCIP may not be approved. If the use of CCIP is approved, the maximum percentage the Owner will consider to cover reimbursable costs to cover all required liability insurance required by the contract documents, CCIP coverage will be 1.0%; and the maximum percentage the Owner will consider as reimbursable costs for all levels of CCIP related worker's compensation insurance will be 1.0%. The Cost of Work these percentages will be applied to will only be reimbursable CMAR costs not including the cost of CCIP or the CM's Fee. The maximum allowed CCIP %'s will be considered to cover any CCIP claim deductible costs and the costs incurred to settle any CCIP claims. CM will need to provide documentation of CCIP coverage from their CCIP provider(s). | 0% | If CM is interested in proposing to use CCIP to provide the contractually required liability insurance covering the prime contract and all eligible levels of trade contractors , please enter 1.0% or a lower percentage in the box to the left. (Or Enter N/A if applicable)
Line 12.B | See Note in Line 12.A | 0% | If CM is interested in proposing to use CCIP to provide the contractually require worker's compensation insurance covering the prime contract and all eligible levels of trade contractors , please enter 1.0% or a lower percentage in the box to the left. )Or enter N/A if applicable.)
Note on B1: Replace Red XXXs by Entering Name of DISD Project
Note on D1: Replace Red XXXs with the Name of CMAR submitting this Proposal
Note on C3: This cell will automatically post the grand total of all Preconstruction Services in Tab 1.A
Note on C4: This cell will automatically post the grand total of all costs estimated in Tab 1.B.
Note on C5: This cell will automatically post the grand total of all costs estimated in Tab 1.C.
Note on C12: This amount should be entered by the Owner and should be the budget number provided by the Owner. The CMAR should assume this CMAR GMP Budget included all contingency amounts to be approved.

## Tab 1.A Preconstruction
Proposed Preconstruction Services fees By Phase
Description of Preconstruction Services and GMP Development Services to Be Provided per DISD A133 Agreement. Articles 3.1 thru 3.1.14 and Article 3.2.1 thru 3.2.10. Refer also to specific preconstruction related responsibilities included in the narrative included in the DISD RFP document which will be incorporated by reference in the A133 contract Agreement. This Preconstruction Services lump sum price proposal covers all Preconstruction Phase and GMP development deliverables expected by DISD. | Total Proposed Amount to be Charged by CMAR for Contractually Required Preconstruction Phase and GMP development Services. Note: The DISD RFP for this project anticipates the CM starting preconstruction services prior to 50% CD's | Breakout Amount for Estimated Lump Sum Charge for Deliverables to be Completed before and during SD Phase of Design | Breakout Amount for Estimated Lump Sum Charges for Deliverables to be Completed Prior to 50% CD's | Breakout Amount for Estimated Lump Sum Charges for Deliverables to be Completed in connection with review of 50% CD Phase of Design Docs | Breakout Amount for Estimated Lump Sum Charge for Deliverables to be Completed in connection with 95% CD Phase of Design Docs | Breakout Amount for Estimated Lump Sum Charge for Deliverables to be completed in connection with review of 100% CD Phase of Design Docs | Breakout Amount for Estimated Lump Sum Charge for Deliverables to be Completed in connection with Review of Final CDs. | Breakout Amount for Estimated Lump Sum Charges for Deliverables Completed during GMP #2 Development Stage of the Project | Breakout Amount for Estimated Lump Sum Charges for Deliverables Completed during GMP #3 Development Stage of the Project | Breakout Amount for Estimated Lump Sum Charges for Deliverables Completed during GMP #4 Development Stage of the Project | Total Lump Sum Charges over the Life of Precon Services and GMP Development Services
3.1.1 Extent of Responsibility The Construction Manager shall exercise reasonable care in performing its Preconstruction Services. The Owner and Architect shall be entitled to rely on, and shall not be responsible for, the accuracy, completeness, and timeliness of services and information furnished by the Construction Manager. The Construction Manager, however, does not warrant or guarantee estimates and schedules except as may be included as part of the Guaranteed Maximum Price. The recommendations and advice of the Construction Manager concerning design alternative and potential cost savings shall be subject to the review and approval of the Architect, Owner, and the Owner’s professional consultant. The Construction Manager is not required to ascertain that the Drawings and Specifications are in accordance with applicable laws, statutes, ordinances, codes, rules and regulations, or lawful orders of public authorities, but the Construction Manager shall promptly report to the Architect and Owner any nonconformity discovered by, or that reasonably should have been discovered by, or made known to the Construction Manager as a request for information in such form as the Architect may require. | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A
§3.1.3 Consultation 3.1.3.1 The Construction Manager shall schedule and conduct meetings with the Architect and Owner to discuss such matters as procedures, progress, coordination, and scheduling of the Work | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1.3.2 The Construction Manager shall advise the Owner and Architect on proposed site use and improvements, selection of materials, building systems, and equipment. The Construction Manager shall also provide recommendations to the Owner and Architect, consistent with the Project requirements, on constructability; availability of materials and labor; time requirements for procurement, installation and construction, which shall satisfy Owner’s time requirements; prefabrication; and factors related to construction cost including, but not limited to, costs of alternative designs or materials, preliminary budgets, life-cycle data, and possible cost reductions. The Construction Manager shall consult with the Architect regarding professional services to be provided by the Construction Manager during the Construction Phase. | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
§ 3.1.3.3 The Construction Manager shall assist the Owner and Architect in establishing building information modeling and digital data protocols for the Project, using AIA Document E203™–2013, Building Information Modeling and Digital Data Exhibit, to establish the protocols for the development, use, transmission, and exchange of digital data. | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1.3.4 During the Preconstruction Phase, the Construction Manager shall review the Contract Documents to ascertain whether the components of the plumbing, electrical and mechanical systems may be constructed without interference with each other, or with the structural or architectural components of the Project, or with existing systems. In the event that conflicts between the systems are discovered, the Construction Manager shall promptly notify the Owner and Architect in writing. | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1.3.5 Notwithstanding any provision of the General Conditions of the Contract for Construction to the contrary, the Construction Manager shall not be entitled to additional compensation for any delay or disruption to the Work arising from any conflict between the mechanical, electrical, and plumbing systems with each other, or with the structural or architectural components of the Work, or with existing systems, if such conflicts should have been discovered during the Construction Documents Phase by the Construction Manager through the exercise of reasonable diligence, and the Owner and Architect were not informed of such conflicts as required by subparagraph 2.1.2.1. This provision shall apply only with respect to conflicts appearing in the Drawings and Specifications provided for the Construction Manager's review prior to proposal of a Guaranteed Maximum Price. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
3.1.14 Project Schedule When Project requirements in Section 4.1.1 have been sufficiently identified, the Construction Manager shall prepare and periodically update a Project schedule for the Architect’s review and the Owner’s acceptance. The Construction Manager shall obtain the Architect’s approval for the portion of the Project schedule relating to the performance of the Architect’s services. The Project schedule shall coordinate and integrate the Construction Manager’s services, the Architect’s services, other Owner consultants’ services, and the Owner’s responsibilities; and identify items that affect the Project’s timely completion. The updated Project schedule shall include the following: submission of the Guaranteed Maximum Price proposal; components of the Work; times of commencement and completion required of each Subcontractor; ordering and delivery of products, including those that must be ordered in advance of construction; dates of Substantial Completion and Final Completion; and the occupancy requirements of the Owner. If updated Project schedules indicate that previously-approved schedules may not be met, then the Construction Manager shall make appropriate recommendations to the Owner and Architect and, upon written approval of both, shall implement necessary corrective action. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.15 Phased Construction - The Construction Manager, in consultation with the Architect, shall provide recommendations with regard to accelerated or fast-track scheduling, procurement, and sequencing for phased construction. The Construction Manager shall take into consideration cost reductions, cost information, constructability, provisions for temporary facilities, and procurement and construction scheduling issues. The Construction Manager shall make recommendations to the Owner and Architect regarding the phased issuance of Drawings and Specifications so as to facilitate the proposal of a Guaranteed Maximum Price when all elements of the Drawings and Specifications are at least ninety percent complete, unless mutually agreed otherwise by the Architect, Owner and the Construction Manager. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.6 Cost Estimates § 3.1.6.1 Based on the preliminary design and other design criteria prepared by the Architect, the Construction Manager shall prepare, for the Architect’s review and the Owner’s approval, preliminary estimates of the Cost of the Work or the cost of program requirements using area, volume, or similar conceptual estimating techniques. If the Architect or Construction Manager suggest alternative materials and systems, the Construction Manager shall provide cost evaluations of those alternative materials and systems. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
§ 3.1.6.2 As the Architect progresses with the preparation of the Schematic Design, Design Development and Construction Documents, the Construction Manager shall prepare and update, at appropriate intervals agreed to by the Owner, Construction Manager and Architect, an estimate of the Cost of the Work with increasing detail and refinement. The Construction Manager shall include in the estimate those costs to allow for the further development of the design, price escalation, and market conditions, until such time as the Owner and Construction Manager agree on a Guaranteed Maximum Price for the Work. The estimate shall be provided for the Architect’s review and the Owner’s approval. The Construction Manager shall inform the Owner and Architect in the event that the estimate of the Cost of the Work exceeds the latest approved Project budget, and make recommendations for corrective action and/or cost reductions, including but not limited to, substitution of materials or revisions or alterations to the Design Development Documents or the Construction Documents, to bring the Project within the Owner’s budget, but shall not delete necessary components of the Project without consent of the Superintendent of Schools or designee. In the event that the quality or scope identified in the estimates are unacceptable or exceed the Owner’s identified budget, the Construction Manager shall work with the Architect to develop options that are acceptable to Owner and are within the Owner’s budget. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
§ 3.1.6.3 If the Architect is providing cost estimating services as a Supplemental Service, and a discrepancy exists between the Construction Manager’s cost estimates and the Architect’s cost estimates, the Construction Manager and the Architect shall work together to reconcile the cost estimates. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
§ 3.1.7 As the Architect progresses with the preparation of the Schematic Design, Design Development and Construction Documents, the Construction Manager shall consult with the Owner and Architect and make recommendations regarding constructability and schedules, for the Architect’s review and the Owner’s approval. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
§ 3.1.8 The Construction Manager shall provide recommendations and information to the Owner and Architect regarding equipment, materials, services, and temporary Project facilities. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
§ 3.1.9 The Construction Manager shall provide a staffing plan for Preconstruction Phase services for the Owner’s review and approval. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
§ 3.1.10 If the Owner identified a Sustainable Objective in Article 1, the Construction Manager shall fulfill its Preconstruction Phase responsibilities as required in AIA Document E234™–2019, Sustainable Projects Exhibit, Construction Manager as Constructor Edition, attached to this Agreement. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
§3.1.11 Subcontractors and Suppliers 3.1.11.1 If the Owner has provided requirements for subcontractor procurement in section 1.1.14, the Construction Manager shall provide a subcontracting plan, addressing the Owner’s requirements, for the Owner’s review and approval. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
§ 3.1.11.2 The Construction Manager shall develop bidders’ interest in the Project. To the extent not inconsistent with the Construction Manager’s requirements under Texas Government Code Chapter 2269, Subchapter F, the Construction Manager shall seek to develop subcontractor interest in the Project and shall furnish to the Owner and Architect for their information a list of possible subcontractors, including suppliers who are to furnish materials or equipment fabricated to a special design, from whom proposals will be requested for each principal portion of the Work. The Architect will promptly reply in writing to the Construction Manager if the Architect or Owner know of any objection to such subcontractor or supplier. The receipt of such list shall not require the Owner or Architect to investigate the qualifications of proposed subcontractors or suppliers, nor shall it waive the right of the Owner or Architect later to object to or reject any proposed subcontractor or supplier. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
§ 3.1.11.3 The processes described in Article 9 shall apply if bid packages will be issued during the Preconstruction Phase. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
§3.2 Guaranteed Maximum Price Proposals 3.2.1 thru 3.2.10 Guaranteed Maximum Price Proposal (s) Refer to A133 contract document for details or Requirements to be delivered during GMP Development Stage. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grand Total Proposed Lump Sum for Preconstruction & GMP Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note: Insert any line additional items necessary to accommodate the Preconstruction Deliverables included in the DISD RFP document issued for this project.

## Tab 1.B CMAR Staff Costs
CMAR Staff or Consultants Expected to Provide Reimbursable Construction Phase Services - List by Position and/or Function. Only Include Positions that are Allowable per the A133. Add or delete row as necessary. Note: Include CM Foremen if they are expected to vehicle allowance or company provided vehicle. | Construction Phase Work (Note Do Not Include and Time Spent Performing Agreed Upon Preconstruction Services. Only Include projected billable time by CMAR Staff of Consultants Performing Construction Phase Staff Services.) | Name of Proposed Reimbursable Personnel or Consultants (or TBD If Name Not Known) | Estimated Months to be Billed During Construction Phase of Project by Year | Estimated Billable Hours Per Month Worked Month - Do Not include PTO Hours | Total Estimated Billable Construction Phase Hours by Year (Col D x Col E) | Estimated Actual Costs Per Hour of Base Wages plus allowable payroll taxes, worker's compensation insurance, and fringe benefits including estimated costs of allocable time related to Paid-Time- Off (PTO) | If Applicable: Estimated Costs Per Hour for Auto Allowance or company Provided Vehicle Including fuel and other reimbursable expenses | Total Staff Cost per hour for Base Wages, Payroll Taxes, W/C Insurance, Fringe Benefits Including PTO and Cost of Vehicles where applicable (Col G + Col H) | Total Proposed Not-To Exceed CMAR Staff and Consultant Costs for Labor/Labor Burden/Vehicle Allowances/Company Provided Vehicle Costs from Construction Phase Notice to Proceed to Project Close-out
Senior Project Manager | 2027 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Manager | 2027 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Assistant Project Manager | 2027 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Superintendent | 2027 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Assistant Project Superintendent | 2027 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Engineer | 2027 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Field Engineer | 2027 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
On-site Clerical Assistance | 2027 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scheduler (for project specific time only) | 2027 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Safety Coord. )for project Specific Time Only) | 2027 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sr. Estimator | 2027 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Estimator | 2027 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Senior Project Manager | 2028 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Manager | 2028 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Assistant Project Manager | 2028 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Superintendent | 2028 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Assistant Project Superintendent | 2028 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Engineer | 2028 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Field Engineer | 2028 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
On-site Clerical Assistance | 2028 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scheduler (for project specific time only) | 2028 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Safety Coord. )for project Specific Time Only) | 2028 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sr. Estimator | 2028 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Estimator | 2028 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Senior Project Manager | 2029 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Manager | 2029 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Assistant Project Manager | 2029 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Superintendent | 2029 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Assistant Project Superintendent | 2029 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Engineer | 2029 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Field Engineer | 2029 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
On-site Clerical Assistance | 2029 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scheduler (for project specific time only) | 2029 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Safety Coord. )for project Specific Time Only) | 2029 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sr. Estimator | 2029 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Estimator | 2029 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Totals |  |  | 0 | 0 | 0 |  |  |  | 0
Note on G1: Do not include any non-reimbursable costs per the A133...such as Incentive pay (e.g. bonuses), ESOP plan costs, stock awards, etc.)

## Tab 1.C - Non-Staff GC-GR Costs
Estimated other Costs to Be Incurred by CM from Construction Phase Notice to Proceed through Project Close-Out. Note: Post Close-out CM Warranty Costs are not reimbursable and are to be considered by the CM Fee. Add or delete lines as necessary. | Estimated Months From Construction Phase Notice to Proceed thru Project Closeout | Estimated Hours Per Month for Labor or Equipment - DO Not include PTO Hours. Also do not include any costs intended to be covered in Tab 1.B. | Estimated Hourly Labor and Labor Burden Costs for Non-Staff CM Labor or Estimated Hourly Rate for CM Provided Equipment | Estimated Reimbursable CM Direct Non-Staff Labor and Labor Burden Costs (Col C x Col D) | Estimated Material Costs | Equipment: Note: Contractual Limits on Monthly Rates and Overall Cap at 50% of FMV of Equipment (Including Allowable PC Hardware, etc.) (Col C x Col D) | Other Costs | Subcontract Costs | Total Estimated Costs Othe Reimbursable CM costs usually described as general conditions or general requirements. Refer to Owner A133 Agreement for Definition of Reimbursable and Non-Reimbursable Costs
General Cleaning performed by CM labor or subcontract labor on T&M basis. |  |  |  | 0 | 0 | 0 |  |  | 0
Charges for PC's Used by Reimbursable CM Staff |  |  |  | 0 | 0 | 0 |  |  | 0
Charges for Tablets Used by Reimbursable CM Staff |  |  |  | 0 | 0 | 0 |  |  | 0
Charges for Mobile Phones Used by Reimbursable CM Staff |  |  |  | 0 | 0 | 0 |  |  | 0
Charges for Reimbursable PC Software Used by Reimbursable CM Staff |  |  |  | 0 | 0 | 0 |  |  | 0
Charges for Authorized Technology such as Procore |  |  |  | 0 | 0 | 0 |  |  | 0
Charges for Authorized Technology such as SIteTraxx |  |  |  | 0 | 0 | 0
Charges for Authorized Technology such as Drone Deploy |  |  |  | 0 | 0 | 0
Charges for Authorized Technology such as Drone Deploy |  |  |  | 0 | 0 | 0
Document printing |  |  |  | 0 | 0 | 0 |  |  | 0
Jobsite Office and storage trailer rental |  |  |  | 0 | 0 | 0 |  |  | 0
Job office furniture, equipment, and expendables |  |  |  | 0 | 0 | 0 |  |  | 0
Job office security and cleaning |  |  |  | 0 | 0 | 0 |  |  | 0
Vehicle costs for onsite CM/GC vehicles |  |  |  | 0 | 0 | 0 |  |  | 0
Postage and Shipping |  |  |  | 0 | 0 | 0 |  |  | 0
Project photos |  |  |  | 0 | 0 | 0 |  |  | 0
Temporary toilets |  |  |  | 0 | 0 | 0 |  |  | 0
Drinking water |  |  |  | 0 | 0 | 0 |  |  | 0
Contractor signage |  |  |  | 0 | 0 | 0 |  |  | 0
Safety equipment for CM/GC personnel |  |  |  | 0 | 0 | 0 |  |  | 0
First aid supplies & Fire Extinguishers |  |  |  | 0 | 0 | 0 |  |  | 0
CM/GC mobilization/demobilization |  |  |  | 0 | 0 | 0 |  |  | 0
Jobsite security |  |  |  | 0 | 0 | 0 |  |  | 0
GM/GC parking/shuttles |  |  |  | 0 | 0 | 0 |  |  | 0
Phone & Internet installation & line charges |  |  |  | 0 | 0 | 0 |  |  | 0
Small tools for CM/GC usage |  |  |  | 0 | 0 | 0 |  |  | 0
Temporary fencing |  |  |  | 0 | 0 | 0 |  |  | 0
Barricades |  |  |  | 0 | 0 | 0 |  |  | 0
Temporary enclosures |  |  |  | 0 | 0 | 0 |  |  | 0
Temporary stairs |  |  |  | 0 | 0 | 0 |  |  | 0
Opening protection |  |  |  | 0 | 0 | 0 |  |  | 0
Safety railings and fall protection |  |  |  | 0 | 0 | 0 |  |  | 0
Weather protection |  |  |  | 0 | 0 | 0 |  |  | 0
Temporary utilities hookup |  |  |  | 0 | 0 | 0 |  |  | 0
Temporary utility bills |  |  |  | 0 | 0 | 0 |  |  | 0
Dumpster Service Fees (Do Not Include Sales Tax) |  |  |  | 0 | 0 | 0 |  |  | 0
Final clean (Usually Performed by Final Clean Subcontractor) |  |  |  | 0 | 0 | 0 |  |  | 0
Flagging/traffic control |  |  |  | 0 | 0 | 0 |  |  | 0
Dust control |  |  |  | 0 | 0 | 0 |  |  | 0
CM Provided Equipment - Such as a Forklift (See Equipment Rate Tab) |  |  |  | 0 | 0 | 0 |  |  | 0
CM Provided Equipment - Such as a Backhoe or Loader (See Equipment Rate Tab for calculation of hourly rate) |  |  |  | 0 | 0 | 0 |  |  | 0
Total Proposed NTE for Other Reimbursable CM Construction Phase Costs |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | Material | Equipment | Other | Subcontracts | Total

## Memo Equip. Rental - Bare Rates
CMAR Provided Rental Equipment Description (Such as (Include loaders, fork lifts, generators, storage trailers, etc.) | List CM Provided Rental Equipment Make/Model/Year (Where Applicable) and Serial # if Applicable | Estimated Fair Market Value (FMV) of Equipment When First Used on the Job | Contractual Bare Rental Note: Cap on total Rentals Equal to 50% of FMV of Equipment when First Used on Job) | Equipment Watch - AED Monthly Rate Adjusted for Location Or Current Monthly Rental Estimate | Max of 75% of Monthly Equipment AED Book Rate (75% of Col E) | Estimated Reimbursable Hourly Bare Rental Costs (Col F div by 173.3)
|  | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0
Note: It is the intent of Owner that the above Contractor Owned Equipment Rental Rates will be subject to audit and adjustment to actual from time to time during over the life of the project per the terms of the A133 CM agreement. Note: The CMAR contract agreement has specific cost limitations of amounts that can be charged for CMAR owned equipment. Insurance, Fuel and minor maintenance will be billed separately at actual costs incurred by CM.